## check IR 135944 Issue in SAR MI
SAR No. | Project Code | Project Name | Vendor Name | Problem Description | Root Cause | Correction | Corrective Action | Action By | Responsible Department | SAR Classification(Engineering Related) | Remarks
3 | JB0947 | Kisan Sahakari Chini mills ltd | Fabrimax Engineering Pvt Ltd | 1. Connecting beam & supporting brackets is mismatching between Column D2-D3 in 90/270 Deg. orientation @ EL+13600mm. | 1. Bracket in D-3 @ EL+13600 in 90 deg. Orientation to be removed completely. 2. new bracket (Type-24) to be supplied to site or fabricated at site. 3. New fabricated bracket to be fixed in D-3 Column to suit ISMB620 section @ EL13600 | 1. Bracket in D-3 @ EL+13600 in 90 deg. Orientation to be removed completely. 2. new bracket (Type-24) to be supplied to site or fabricated at site. 3. New fabricated bracket to be fixed in D-3 Column to suit ISMB620 section @ EL13600 | 1. Bracket in D-3 @ EL+13600 in 90 deg. Orientation to be removed completely. 2. new bracket (Type-24) to be supplied to site or fabricated at site. 3. New fabricated bracket to be fixed in D-3 Column to suit ISMB620 section @ EL13600 | Sunil Kumar Gupta | C & I |  | approved
4 | JB0947 | Kisan Sahakari Chini mills ltd | Fabrimax Engineering Pvt Ltd | 1. Beam mkd.no. 25B006 is fouling with columns due to excess of length by appx. 2800mm. 2.. As per Fabrication Drawing (-042-019) beam shall be fixed in 7800 span (between D3-D4) 3. As per assly & GA drawing Span between D-3 & D-4 shall be 5000mm only. | Beam to be cut to suit the span (5000mm) between D-3 & D-4 | Beam to be cut to suit the span (5000mm) between D-3 & D-4 | Beam to be cut to suit the span (5000mm) between D-3 & D-4 | Sunil Kumar Gupta | C & I | Not a SAR | approved
5 | JB0947 | Kisan Sahakari Chini mills ltd | Fabrimax Engineering Pvt Ltd | 1. HRM112 is mismatching with HRM102 & HRM110 due to height variation. 2. Height of HRM112 is 900mm but height of HRM102 & HRM110 is 1230mm. 3. Same problem comes with HRM111 due to height variation with adjacent handrail. | detail mismatch | use extra handrail provided | detail revised | Sunil Kumar Gupta | C & I | Detail Mismatch | approved
6 | JB0947 | Kisan Sahakari Chini mills ltd | Fabrimax Engineering Pvt Ltd | Beam mkd. No. 14B001 (ISMC250)received at site with 1000mm short in length. As per dwg. length required as 7782mm but actual observed at site as 6782mm. | wrong supply by vendor | NEW BEAM TO BE ARRANGED | avoid | Sunil Kumar Gupta | C & I | Not a SAR | approved
7 | JB0947 | Kisan Sahakari Chini mills ltd | Isgec Heavy Engineering Ltd | 1. Primary Air heater Bottom Tube Plate is fouling with gratings @ EL+6000 resting on beam 06B069 & 06B066. 2. Approx 270 mm portion of tube plate fouling with all gratings on both LHS & RHS of Boiler. | Grating to be cut to suit at site. | Grating to be cut to suit at site. | Grating to be cut to suit at site. | Sunil Kumar Gupta | C & I |  | APPROVED
8 | JB0947 | Kisan Sahakari Chini mills ltd | KMV INDUSTRIES | 1. 05 nos holes for Primary Air Heater-II Bottom Tube Plate found undersize. 2. As per dwg. hole size shall be 65mm but at site it was observed as 62mm. | FABRICATION MISTAKE | Make DIA 64 mm of hole at site and corressponding the 5 nos of tube are to be welded with tubesheet as stay tube. | More vigielence is required during inspection. | ESG Pragasam | Electrical | Item misplaced at site | Approved 100% Go ,No Go test and records should be made available.
9 | JB0947 | Kisan Sahakari Chini mills ltd | Isgec Heavy Engineering Ltd | 1. As per drg no JB0947-50061001-ASY-004/R00 Beam no 20B010(13) shown at EL+22710 But as per drg no JB0947-50060500-004-001/R00 terporary supporting Beam no DLS002 shown as same elevatation(EL+22710) for Mud Drum ereaction . . | Temporary drum lifting was made at later stage. | Drum lifting beam is final beam | lifting structure to be designed earlier | Sunil Kumar Gupta | C & I |  | approved
10 | JB0947 | Kisan Sahakari Chini mills ltd | Isgec Heavy Engineering Ltd | 1. As Per drg front wall pannel (FRP001& FRP002) width req-2816 observed 2806 & 2808 2. Ovality found in Stub OD/ID 4 o 5 in bottom header fo front wall pannel. | It seems to be a fabrication mistake. | Please provide the invidual tube to tube pitch dimension of the panel to provide the solution. | Before erection, trail assembly need to be done. | ESG Pragasam | Construction | Item misplaced at site | 1.Assemble panels on vertical and horizontal. Measure panel dimensions width , length and diagonal. Report maximun pitch which is required to be maintained to manage the deviation for anlysing and accepting the same. 2.It appears from photo that the stub ovality is noticed on ID, This can be grinded and matched with panel stub.
11 | JB0947 | Kisan Sahakari Chini mills ltd | Isgec Heavy Engineering Ltd. | 1. As Per Drg Rear water wall pannel (REP006) width req-2816 observed 2806 2..As Per Drg Rear water wall pannel (REP005) width req-2816 observed 2809 | It seems to be a fabrication mistake. | Please provide the invidual tube to tube pitch dimension of the panel to provide the solution. | Before erection, trail assembly need to be done. | ESG Pragasam | Construction | Item misplaced at site | Please trial assemble all panels in vertical and horizontal.Inform dimensions between fin end to end width and diagonals. Inform maximum pitch (Tube to tube spacing ) attained after assembly for analysing the impact .
12 | JB0947 | Kisan Sahakari Chini mills ltd | Isgec Heavy Engineering Ltd | Primary Super Heater coil No. PSE052 is observed bend in the Middle by 120mm as Shown in attached Snap. | It seems to be fabrication mistake or Erection mistake. | Fouling coils are to be cut and rectify to maintain the distance as per Drg to avoid the gas path abstraction during running of Boiler. | Before Erection, coils alignment to be checked. | ESG Pragasam | Structure | Fouling Problem | The coil at support point can be stretched towards front and rear side to maintain flatness. Seal plate can be locked after maitaining teh flatness. Plaese try and revert
13 | JB0947 | Kisan Sahakari Chini mills ltd | ISGEC HEAVY ENGINEERING LTD. (YNR) | As Shown in attached Photographs, the Economiser Outlet header end plate is not possible to weld, as the beam mkd no. DLS002( Mud Drum temporary suport) Which is erected in place of beam tag No. 22710(13), as per the SAR-09. | This is not a SAR. Because, the shown beam is given for temperavary purpose. | The same has been conveyed to site that the beam to be removed before welding the end plate | This is not SAR | ESG Pragasam | Structure |  | Approved. Temporary support shall be marked and yellow painted.Instruction for removal shall be given in the drawing. 3D modelling to see the weldability check.
14 | JB0947 | Kisan Sahakari Chini mills ltd | Maharaj Engineering Enterprises | As Shown in attached Photographs, The problem is coming in fixing Buckstay beam. The Main problems are: 1.) The gap between buckstay corner plate and beam is required 15mm while it is actually coming is 6-8mm in most of the locations. 2.) The expansion offset for the buckstay corner plate and beam is less or in oppsite direction in most of the locations. 3.) The rear buckstay beam is 25mm higher than LHS beam and the LHS beam is 25mm upper than the front beam. While the it is ok with rear , RHS and Front panel. The dimensions of corner plate, beams are obsereved as per drawing | Buck Stay Fabricator Mistake. | 1. Wher ever the gap is not as per the drawing please cut the (P.No 10 RETAINER PLATE) and the maintain gap as per the drawing. 2. To maitain the dimension given in the drawing.Please and relocate the (P.No 8 Pda Plate). 3. To avoid the 25 mm height differance. cut the lug plate weld in the water wall and to be rewelded at the correct location as per the drawing. if you have any shortage or damage in the lug plate during the modification the new lug plate can be arranged from PED-Yamunanagar. | Shall be thoroughly checked during inspection. | ESG Pragasam | Electrical | Not a SAR | Approved
15 | JB0947 | Kisan Sahakari Chini mills ltd | ISGEC HEAVY ENGINEERING LTD. (YNR) | As Shown in attached Photographs, a gap of 50mm is obserevd while fixing the Spool piece tag no IFP016 and IFP017 with Rear bottom header and IFP015 and IFP014 respecively. The reason being observed in the difference in the dimensions of other spool pieces are less by 5-10mm. | Fabrication Mistake | Site suggestion accepted to cut and add 300 mm spool with available spare pipe. | More Vigielence required during Fabrication & inspection. | ESG Pragasam | Construction |  | Approved
16 | JB0947 | Kisan Sahakari Chini mills ltd | Maharaj Engineering Enterprises | As Shown in attached photographs, The Holes in front side Buckstay beam for EL+19750 are wrongly done in Lower side.These holes should be done at upper side. | Fabrication Mistake | Wrongly made holes to be plugged and new holes to be made as per drg at site. | More vigielence required during inspection. | ESG Pragasam | Electrical |  | Approved
17 | JB0947 | Kisan Sahakari Chini mills ltd | ISGEC HEAVY ENGINEERING LTD. (YNR) | Part no 3A for fixing the supports of Super heater coils needed 20nos spare at site but quantity received at site is 262 nos. While the part no 22 ,Plate for fixing the support of super heater are not received at site. But the required quantity needed is 270 nos. | Refered old drgs by site team | Latest Drs has been forwarded to site. | This is not a SAR | ESG Pragasam | Vendor Mistake |  | A mechanisam to see the latest revision of document at site need to be developed online.
18 | JB0947 | Kisan Sahakari Chini mills ltd | ISGEC HEAVY ENGINEERING LTD. (YNR) | As shown in attached photograph, the seal plate part no 14 and 15 are received without primer coating | Vendor sent the item with out painting. | Site suggestion accepted that to do at site. | More vigielence is required for inspection | ESG Pragasam | Electrical |  | Approved
19 | JB0947 | Kisan Sahakari Chini mills ltd | Fabrimax Engineering Pvt Ltd | As per GA of Bank Outlet duct drawing no JB0947-50080400-077-001 Rev 00 The beam( 30B003)at EL +30860 required 4 nos holes for Flue gas sling supports. The received beam is found as per fabrication drawing JB0947-50060200-042-022 Rev00) in which no holes are shown. JB0947-50080400-077-001 & JB0947-50060200-042-022 | no input was provided in mechanical input | proposed solution by site is ok | provide input | Sunil Kumar Gupta | C & I | Detail Missing | approved
20 | JB0947 | Kisan Sahakari Chini mills ltd | ISGEC HEAVY ENGINEERING LTD. (YNR) | The Secondary Super heater coil No 18 is failed in Ball test. The Ball is found struck at bend as shown in attached photograph. The ball size used for ball test is ø25mm ~ 68% of tube ID. Also, The ball of size ø19mm~ 52%of tube ID is freely coming Out from the Bend. | Fabrication Mistake | Site Suggestion Accepted Using the secondary super heater spare tubes. | Shall be thoroughly checked during inspection. | ESG Pragasam | Construction | Item misplaced at site | Approved
21 | JB0947 | Kisan Sahakari Chini mills ltd | K.K.CONSTRUCTION & BUILDERS | As shown in attached photographs, the quality of Fan foundation is very poor. There is level difference of 100mm is obsereved for the C/L of delivery and casing foundations. Also the quality of foundations pocket is very poor. Lot of honeycomb structure are obsereved in the pocket ready for Fan rotor and motor foundation. |  | DETAIL PROVIDED |  | G.Rao |  | Detail Missing
22 | JB0947 | Kisan Sahakari Chini mills ltd | ISGEC HEAVY ENGINEERING LTD. (YNR) | As shown in attached photogrpahs , the quality of Secondary super heater is coil is very poor. Maximum coils are found bend. Some coils are even bend at joint which is because of improper matching at joint. | It seems to be fabrication mistake . | Need to be rectified before erection to match the pitch dimension as per drg. | Fabricated equipment or materials need to be checked before dispatch. | ESG Pragasam | Construction | Item misplaced at site | Coils are not stacked .Please lay the coil in the flat surface and measure teh deviations and report for resolution. A deviation of 3 mm between the tube of coil is acceptable.
23 | JB0947 | Kisan Sahakari Chini mills ltd | ISGEC HEAVY ENGINEERING LTD. (YNR) | As shown in attached photogrpahs , the Edge buttering done at the spoo piece IDP003 of Attemperator piping is very poor quality. Cracks and porous holes are observed at the edge. Around 6-8mm edge is grindout to remove the defects | Fabrication mistake | By grindout to remove the defects crack and to be done DPI test at site. | Before dispatch shall be thoroughly check the material. | ESG Pragasam | Construction | Item misplaced at site | Difficult to asees the quality of pipe used.Cracks may be there in other raeas also. Suggest to replace the stright length with new piece to avoid operational issues.
24 | JB0947 | Kisan Sahakari Chini mills ltd | A.R.Engg.Works | As shown in attached photogrpahs , The cover plates received at site welded with sprag with uniform pitch of 150. While fixing the cover plates, these sprags are touching with the panel bend tube in pneumatic spreader openings. Rf: JB0947-50130100-053-001 & JB0947-50130100-053-002 | Seat Plate Sprag Deatil Drawing Mistake. | Cut the Sparg to avoid the foul with water wall tube as per the site requirement. | Shall be thoroughly checked the detail drawing and standard drawing. | ESG Pragasam | Mechanical Engg | Fouling Problem | Cover plate anchor fixing guidline shall be made
25 | JB0947 | Kisan Sahakari Chini mills ltd | KSB Engineering Works | The total length from MSSV(F35) centre to end of the bypass valve (F36) is 1110mm while the distance between the centre of Main steam ine and LH Side wall tube outer is only 920mm. The actuator of bypass valve will foul with the LHS panel tube.As per layout the orientation of F36 is shown towards paltform side while as per the flow notation mark on the valve, the bypass valve will go towards panel side. | Vendor Drawings not reviewed properly. | Relocate the MSSV By-Pass valve. SMD drawing is attached (dwg no : JB0947-50090100-SMD-0001). | vendor drawing to be checked properly | ESG Pragasam | Mechanical Engg | Fouling Problem | 3d to 2D
26 | JB0947 | Kisan Sahakari Chini mills ltd | ISGEC HEAVY ENGINEERING LTD. (YNR) | As shown in attached photograhs, foreign material, a 23mm thk plate cut from the header for one of the downcomer opening was left inside the header from the vendor shop.The items is observed during theinspection before prehydro flushing. | Fabrication Mistake | Site Suggestion Accepted | 1. More care to be taken in inspection for future project in the shop. 2. During the ground assembly, if the end caps are received only with tack weld, then the same should be removed and check for any foreign material. | ESG Pragasam | Construction | Item misplaced at site | Provide feedback to Shop.
27 | JB0947 | Kisan Sahakari Chini mills ltd | Batliboi Environmental Engineering | As shown in attached photographs, in both SA fan the height of outlet casing access door is very high and From the access door, nowhere is approachable.The access door should be given in near the bottom side of the casing. | Since This Project Repeat of M/s Green Power. This type of SAR not received from M/s Green Power. | Relocate the Manhole Door Location. Fan vendor given the modification drawing for your reference attached drawing. | Future project will be take care. | ESG Pragasam | Mechanical Engg | Drawing Mistake | Approved. Should be taken care during design review
28 | JB0947 | Kisan Sahakari Chini mills ltd | K.K.CONSTRUCTION & BUILDERS | As shown in attached photographs, The casting of boiler feed pumps is done in irregular manner. The top layer thickness of the foundations is obsreved 80-100mm and this is not a good engineering practice. The Pockets condition is not also not good.The BFP foundations with this type of practice is not acceptable. | BFP foundation top layer level is not good finishing and inside the pocket also. | Inform civil contractor will be corrected the foundation level as per the drawing. | Further, we will informed to site to take care. | ESG Pragasam | Vendor Mistake | Concept Incorrect | Approved
29 | JB0947 | Kisan Sahakari Chini mills ltd | Project Aiders | As shown in attached photographs, The 1 no. bagasse silo is found twisted all over the height. While The Feeder alignment is OK and the matching of the silo at the feeder is OK but when we see for the top it was found twisted.The reason is during the manufacutring stage, the diagonals are not maintained properly. JB0947-50221100-ASY-001 JB0947-50221200-206-002
30 | JB0947 | Kisan Sahakari Chini mills ltd | Isgec Covema Ltd. | As shown in attached photographs, The gap between the thermowell of primary super heater I/L Header and Top supported beam is only 90mm. The thermowell is mkd for temperature test pockets (TTP401) which is not possible to fix. JB0947-50030100-027-001 R1 JB0947-50990200-PID-004 R1 JB0947-50061000-ASY-021 R0 | The gap is less between the thermowell of primary super heater I/L Header and Top supported beam. | 36 mm dia hole to be drilled in top support beam. Refer the attached Drawing JB0947-50030100-SMD-0003 | Since, this is repeat project. we have released the same drgs. Hereafter,As per guidline, the thermowell will be provided on staem line not in the header 3D modelling can resolve such issues | ESG Pragasam | Mechanical Engg | Drawing Mistake | Approved
31 | JB0947 | Kisan Sahakari Chini mills ltd | Isgec Heavy Engineering Ltd | As per P&I diagram, 8Nos dampers {(3 nos. FD Discharge Damper(DAM707& 708+709)+ 3nos. SA Discharge Damper(DAM713 & 714 & 715)+ 2 Nos ID damper (DAM725 and 726), the damper are shown with mounting for Limit switches.But the received dampers are not having any Provision for mountings.and also no mounting provision is shown in mechanical drawing, Also, the Limit switches are also not received at site. JB0947-50080100-095-001 to 002 R0 JB0947-50080300-095 -001 to 002 R0 JB0947- 50080400-095-001 R0 JB0947-50990200-PID-007 R1 | Limit switches mounting deatil not provided in damper drawing. | Limit Switch mounting frame detail refer the attached drawing. No JB0947-50080100-SKT-0001. | Future project limit switch mounting frame detail will be provided. Scope matrix has been made and will be circulated to have clarity between engineering teams. | ESG Pragasam | Mechanical Engg | Drawing Mistake | Approved
32 | JB0947 | Kisan Sahakari Chini mills ltd | NGT Engineering Pvt. Ltd. | As shown in attached photogrpahs, the TG Stoker many numbers of chain Links are obsereved offset.The chain is supplied in a combination of 10nos chain links. But in between those chain links some are also obsereved offset, which is creating the chain to move (in tension) one side as shown in the another attached photograph. | fabrication mistake | Defect chain links are to be replaced by correct one. | QC to be check | Prasenjit Chakrabarti | Electrical | Not a SAR | Inspection to be done by asseblying the Chain links.
33 | JB0947 | Kisan Sahakari Chini mills ltd | gangaram contractor | blank
34 | JB0947 | Kisan Sahakari Chini mills ltd | AVN Engineer tech | The PCD of holes for fixing in the Stuffing box of CE and GD rapping system is obsereved 125mm but on the mounting brackets of the frame, it is observed 145mm.while as per drawing, the PCD is given 145mm. AS0040-68080100-408--003 R0 AS0040-68080100-410--003 R0 | Vendor/QC problem | New flanges will be supplied to site | One off case | Gururaja Rao | Process | Not a SAR | -
35 | JB0947 | Kisan Sahakari Chini mills ltd | Sitson India Pvt. Ltd. | As per Vendor Drawing( JB0947-50490100-VEN-001 R1), the Long retractable soot blowersupport arangement is shown by two adjustable screw. While as per soot blower supports drawing(JB0947-50100300-129-001 R0), it is that adjustable hook support.and material is received as per support drawing but on the LRSB, there is no provision to mount the hook. B0947-50100300-129-001 R0 JB0947-50490100-VEN-001 R1 | Long Retractable Soot Blower Support detail mismatch. | Soot Blower Support welding detail refer attached drawing no:JB0947-50100300-SMD-0001 | Shall be throughly check with Vendor Drawing. | ESG Pragasam | Mechanical Engg | Not a SAR | Approved
36 | JB0947 | Kisan Sahakari Chini mills ltd | Isgec Heavy Engineering Ltd | JB0947-50090100-104-001 A4/DLG-920-606/N9-9P/01Probelm Description: The RHS, Level Gauge will foul with the Economiser O/L to steam Drum I/L Piping. The Gap between the tapping and Pipe Line is580 only while the level gauge mounting is 600mm.and the 500mm bend portion will foul with the vertical pipe of Feed line. Also, for LHS & RHS root valve piping, is also fouling with the Bracket mounted on E 2 & E3 at 2700 and 900 orientation respectively.
37 | JB0947 | Kisan Sahakari Chini mills ltd | Hi-Tech Systems & Services Ltd. | As shown in attached photographs, the Level gauge is damaged by mechanical contractor. The gauge location is observed totally offset from the centre JB0947-50090100-104-001 A4/DLG-920-606/N9-9P/01 | Site (Mechanical Contarctor) mishandling | Recalibration and reparing to be required at vendor works. | Require Proper and safe Storage of all the materials . Also proper baricades and marking at yard of site from safety deptt. | A. Sajjan | Civil |  | ok
1 | JB0994 | EMAMI AGRO | Emami Agrotech | TOP elevation of all the ESP Structure Columns is observed +350mm including grouting to be done instead of +300mm including grouting is required as per our drg. Top of foundation bolts is also maintained 200 mm instead of 150mm required. Pl suggest Skech of actually measured dimention are attached. | Client mistake during casting | Chipping to be done as per drg. | - | Gururaja Rao | Client |  | -
2 | JB0994 | EMAMI AGRO | HI-TECH ENGINEERING & PROJECTS | We observed that temporary ladders are welded with Boiler # 01, Boiler #02 and Esp #01structure columns instead of clamping arrangement.we have attach some photograph for reference. | old practices followed by the contractor |  |  |  | Construction
3 | JB0994 | EMAMI AGRO | Dummy | We observed that many lot of Economiser coils and superheater coils are bend during unloading at site and also coils are not properly stacking .we have attach some photograph for reference. | Coil damage during transportation / handling | Eco. & SH colils has to be suitably rectified at site as per procedure. |  | K.V.Anguraju | Others
4 | JB0994 | EMAMI AGRO | Dummy | We observed that Furance opening area all around concrete from column center to opening 'X' and 'Y 'is not maching with the drawing .As per drawing from B1,B2 & C1,C2 column to opening distance is 650 mm. But actual distance found at site form column B1,B2 to opening is 622 mm & column C1,C2 to opening distance is 676 mm.Hence front wall header stool tag no IP01B may obstruct to the air box. | Client has not maintained the firing floor concrete cutout dimension as per our input sketch | Chip the RCC tie beam face where ever required for maintaining the following, 1.Centre line of air box inline with column centre line. 2.Centre line of furnace inline with column centre line. 3.All other required dimension w.r.to centre line of column to be maintained as per our drawing. | Client has to make the firing floor concrete cutout as per our input sketch. | K.V.Anguraju | Client |  | Approved.
5 | JB0994 | EMAMI AGRO | Meeco Engineering | Mismatching has been observed in the drawing, for connecting beams in between columns tag no B2toB3&B3toB4. As per drawing no JB0994-50060100-048-007,008 & JB0995-50060100-048-006-Rev-00 at EL+12500 Connecting for B2 to B3 & B3 to B4 dimensions is 300mm, another drawing no JB0994-50061000-ASY-0005-Rev-00 is connecting beam dimension 250 mm . Material received as per JB0994-50061000-ASY-0005-Rev-00 and beam erection and welding are completed. Now the level (-50) difference is observed. After that top of beam level -50 mm found. | mistake | Top level of beam shall be maintained by providing packing and welding it properly with moment bracket and beam. As the beam under consideration is having a stair support so please maintain El +12500. | mistake to be avoided | Sunil Kumar Gupta | Structure | Drawing Mistake | approved
6 | JB0994 | EMAMI AGRO | HI-TECH ENGINEERING & PROJECTS | Material storage condition at Emami Agrotech Site is very poor & some items under open storage shall not properly kept in an elevated location they shall stored directly on ground, when the rain falls contineously one days the presure part & structure material which was already reached at site more then 20 % was merged under water.Still now three times it was happened & after repeated information to Contractor they are not taking any serious action . Some photos are attached for your kind reference | Improper storage |  |  |  | Construction
7 | JB0994 | EMAMI AGRO | HI-TECH ENGINEERING & PROJECTS | Insulation material storage condition at Emami Agrotech Site is very poor. Insulation bag are not protected for rain & also under open storage shall not properly kept in an elevated location they shall stored directly on ground, . Some photos are attached for your kind reference.
8 | JB0994 | EMAMI AGRO | Dummy | We observed that boiler feed pump foundation elevation & dimension are mismatch as per drawing.As per drawing column no DV1,DV2 to foundation distance is 1800 mm but actual 1850 mm found and also TOC level is EL+250 mm as per drawing but actual EL+200 mm found at site. please suggust.
9 | JB0994 | EMAMI AGRO | HI-TECH ENGINEERING & PROJECTS | As per drawing No.JB0994-50030100-031-0001 from both side wall to PSH Coil distance 150mm & SSH coil 250mm. But actual distance found at site from left side wall to PSH Coil distance is 150 mm and right side wall to coil distance.is 118 mm .Also left side wall to SSH Coil distance is 250 mm and right side wall to coil distance.is 218 mm.Another problem is roof wall to coil clear gap is 72 mm but actual found 45 mm. Please Suggust.
10 | JB0994 | EMAMI AGRO | HI-TECH ENGINEERING & PROJECTS | Temporary support directly weld with water wall panel & integral piping for scafolding work . After repeated information to Contractor they are not taking any serious action . Some photos are attached for your kind reference.
11 | JB0994 | EMAMI AGRO | HI-TECH ENGINEERING & PROJECTS | We Observed that structure main column to connecting beam & bracing field weld rusting now in verious locating at boiler & ESP due to not applying the primer paint after finish weld. After repeated information to Contractor they are not taking any serious action . Some photos are attached for your kind reference.
12 | JB0994 | EMAMI AGRO | HI-TECH ENGINEERING & PROJECTS | As per drawing No.JB0994-50030100-031-0001 RHS & LHS wall top header to PSH coil clear gap is 21.4 mm both side but we observed that clear gap are both side wall top header to PSH coil are 10mm to11 mm found.Please Suggust.
1 | JB0995 | EMAMI AGROTECH | Emami Agrotech | We observed that Furance opening area all around concrete from column center to opening 'X' and 'Y 'is not maching with the drawing .As per drawing from B4,B5 & C4,C5 column to opening distance is 650 mm. But actual distance found at site form column B4,B5 to opening is 635 mm & column C4,C5 to opening distance is 660 mm.Hence front wall header stool tag no IP01B may obstruct to the air box.And another problem are top of concrete level ( EL-50 to -80 mm) found at all around of furance opening of jb0994 & jb0995.and we are providing the shim plates to maintain the level. | Client has not maintained the firing floor concrete cutout dimension as per our input sketch | Chip the RCC tie beam face where ever required for maintaining the following, 1.Centre line of air box inline with column centre line. 2.Centre line of furnace inline with column centre line. 3.All other required dimension w.r.to centre line of column to be maintained as per our drawing. and provide packing plates (welded with each other and welded with hdr. support stool base plate) to maintain the bottom header elevation as per our drawing. | Client has to make the firing floor concrete cutout as per our input sketch. | K.V.Anguraju | Client |  | Approved.
2 | JB0995 | EMAMI AGROTECH | ISGEC ENGINEERING AND PROJECTS LTD. | We observed that economoser inlet header drain fouling with economiser bottom supporting structure, beam mark no. 7EB02(03).& Same problem will be faced for boiler No 01 economiser inlet header .Please suggust. | Economiser drain line not interfaced with eco. support tie | Header cl. to end of drain stub shall be maintained as 87mm | Checker/Draftmen are advised to interface properly | K.V.Anguraju | Mechanical Engg | Drawing Mistake | Approved.
1 | JB0996 | IOCL ,Guwahati | Desfab Engineers Pvt. Ltd. | Contractor has till date not provided wooden sleepers for the proper stacking of structure material of boiler & ESP. Material is lying on the ground & not properly stacked. | Improper storage | To be arranged by contractor |  |  | Construction
2 | JB0996 | IOCL ,Guwahati | Isgec Heavy Engineering Ltd | All the water wall panels which are received at site till date have already started getting rust. Some panels which have come within a month have also started getting rust. This might be due to poor blasting & painting at suppliers end | Poor Workmanship of Painting . | To be Repainted at site | Taken up with YNR. |  | YNR
3 | JB0996 | IOCL ,Guwahati | Udehra Mechanical Works | As per drawing no. JB0996-50060100-048-0001 Rev.00, Released qty. of bolts (Mark no. CFT004) is 40 no›œRs & we have received 40 no›œRs. at site also. But as per our column drawing required quantity of bolts for assembly of 04 columns (A3, A4, B3 & B4) is 48 no›œRs. 08 no›œRs are missing in BOM in drawing. So the work for assembly of column has stopped. | Drawing mistake | Additional qty sent to site |  |  | Structure | Drawing Mistake
4 | JB0996 | IOCL ,Guwahati | Isgec Heavy Engineering Ltd | Please refer Plot plan JB0996 - 50990100 - ASY - 0002 Rev 08 co ordinate points mentioned X axis 370.29 and Y axis 840.78 and Foundation plan for boiler DWG No: JB0996 - 50990100 - STR 01 REV 03 co ordinate points mentioned in X axis 370.29 and Y axis 835.78. Due to mismatch of co orninate points work held up at site. Please review and confirm from H.O. | Clarification Only |  |  |  | Not a SAR
5 | JB0996 | IOCL ,Guwahati | Isgec Heavy Engineering Ltd | As per confirmation given to site by the projects departement on 05.05.2017 through mail, they asked site to proceed for the bar bending & cutting as per the drawing no. JB0996-50990100-STR-01 Rev.02 which was approved in CAT-B by STEAG. So going by the confirmation we have completed the bar beding & cutting as per the drawing of REV.02. BUT now we have received the Rev. 03 which is approved in CAT-Ain which elevation has ben increased by 300mm i.e 3.3 Mtr. instead of 3.0 Mtr. So quantity of excavation & modification for vertical reinforcement to be done based on the latest revision. | Clarification Only |  |  |  | Not a SAR
1 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Pennar Industries Ltd. | AIR PREHEATER TUBE ITEM NO. AHT001 & AHT002, LENGTH FOUND 4564 mm INSTEAD OF 4534 MM AS PER DRAWING. DUE TO THIS, TUBE PROJECTION IS COMING 80MM IN FIRST BLOCK OF APH INSTEAD OF 50MM AT COLD END | As per PO no - P10117060 the specified length is 4563 mm only . Supplied material is found ok. | We propoased 80mm projection at cold air entry side and refer the attached sketch. |  | ESG Pragasam | Materials |  | Approved
2 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Star Applied Mechanics (P) Ltd. | During APH preassembly, we found that finishing/machining of tube sheet holes are not proper. Tool marks and metal scrap found on holes. Photos attached for ref. | Poor Workmanship & Visual inspection Miss outs | Grinding to be done properly at site . | Taken up with the Vendor & Inspetcor to be more careful in future. | ESG Pragasam | Vendor Supply & Inspection |  | Ganga Prasad
3 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Gellile Industries | Beam item no. 27B016, 27BT01 & 27BT03 lenght found 200 mm short against revised drawing requirement. | late input from mechanical deptt. | as per site suggestion | later revisison to be avoided | Sunil Kumar Gupta | Mechanical Engg | Late Revision | Approved
4 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Bharat Machine Tools | Sling rod support (SLG061 - Front wall roof tube support-1) location is showing in drawing 1600mm towards rear from column Grid C but it should be from column grid B. 2. Sling rod support (SLG067 - Front wall roof tube support-2) location is showing in drawing 2200 mm toward front from column Grid D but it should be from column grid C. | Sling rod reference point is wrongly mentioned | Modification drawing has been attached (JB0998-50020700-SKT-0001 & 0002) | Throughly reviewd before drawing release. | ESG Pragasam | Mechanical Engg | Drawing Mistake | Approved
5 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Gellile Industries | Head room between drum floor and tie beam item no. 30B002 @ EL+30230 mm found insufficient. | headroom problem | beam to be cut at site as discussed with site incharge, drawing revised | fouling should be avoided | Sunil Kumar Gupta | Structure | Fouling Problem | approved
6 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | EMCEE ENGINEERING WORKS | As per foundation drawing, the foundation bolt centre distance for boiler column B1 & C1 is 600 x 600 mm. But as per structural drawing for column B1 & C1, the centre to centre distance of foundation bolt holes on column base plate shown as 600 x 700 mm. Photograph attached for reference. | drawing mistake | As per site suggestion | mistake to be avoided | Sunil Kumar Gupta | Structure | Drawing Mistake | approved
7 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | ISGEC HEAVY ENGINEERING LTD. (YNR) | In Spool no. ISP002 and IS007, item no. 7 (45° elbow) was wrongly fitted with item no. 3 in shop. As per drawing rolling of item no. 7 should be in left side but it was fabricated towards down. (Photos of received material attached herewith). | Wrong Fabrication | As per site proposal Elbows in both spool piece have to be cut and rewelded as per drawing is accepted. | Taken up with YNR | ESG Pragasam | YNR |  | Approved
8 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Isgec Heavy Engineering Ltd | During alignment of front & rear wall common top header, found that left and right side sling rodes are not vertical due to veriation in dimension of TSB(TSB012) hole to hole distance with respective to front & rear wall common top header lifting lugs to lugs distance. TSB012 hole centre to hole centre distance from right to left is 854mm, 950mm, 950mm & 854mm respectively. Lifting lugs of common top header centre to centre distance from right to left is 900mm, 950mm, 950mm & 900mm respectively. Because of above mentioned distance veriation both end side sling rode are coming inclinde. Photos attached. | Front & rear wall common top header lifting lug location is mismatch with top supporting structure hole location | As per siite suggestion is accepted. Hole distance on tie beam TSB012 shall be shift to match with common top header lifting lugs | Proper structure input to be provide in future. If after structure input any changes immeditely to be inform to consern structure person. | ESG Pragasam | Mechanical Engg | Detail Mismatch | Approved
9 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | EMCEE ENGINEERING WORKS | Moment bracket (TYPE-Z) on column C-3 at EL+7200 in right side of column is hindering in walkway. Moreover, this bracket not at all required as no beam is coming on this bracket. Photos attached. | Drawing not referred properly | Moment bracket to be fixed as per drg.. |  |  | Construction
10 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Gellile Industries | Bracing no. BVBR06 & BVBR07 (Bracing along Brid -B) fouling with front wall panel buckstay BUC201 at elevation EL+16050. | Fouling with buckstay | After remoal of baracing, provide moment connection for 16B012 @ EL +16550 by welding top and bottom flanges of beam to column on both side. | fouling should be checked during mechanical input | Sunil Kumar Gupta | Mechanical Engg | Fouling Problem | approved
11 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | ISGEC HEAVY ENGINEERING LTD. (YNR) | Expansion crimps of evaporator bank assembly are fouling with buckjstay at EL+25150 both LHS & RHS. | Expansion crimps of evaporator bank assembly are fouling with buckjstay at EL+25150 both LHS & RHS. | As per site proposal, Notch cutting of 10 mm made on buckstay plate is accepted. | Future will be taken care | ESG Pragasam | Mechanical Engg | Fouling Problem | Approved
12 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | VAISHNAV ENGINEERING | Item code SPC084, Part no. 5 (manhole plates) wrongly welded inside of part no. 4. Because of this, manhole frame was coming in flue gas path. Item code SPC084 should be in miror image of SPC081 but i was received same as SPC081. Photo attached. | Fabrication & Inspection mistake | As per site proposal, Man hole plates to be cut and re-weld as per drawing is accepted. | 1.Vendor inspection to be taken care in future 2. Drawing also to be made more clarity - in Detail view. | ESG Pragasam | Vendor Supply & Inspection |  | Loganathan
13 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Invenio Engineering | FD air duct item no. FDA007 & FDA019 received as per old revision(Rev. 00). Because of this, FD bypass duct connections were not matching. | Latest Drawing not send to Supplier . Material Supplied by Old Rev 0 dated 31.03.17, Rev 01 - Dated 31.05.17. As per latest Rev PO - P10119066 - dated 14.07.17 Still the Reference drawing is shown as R0 only. Inspection Report dated 25.07.17 . Rep no 1042 - 250 | As per site proposal, cut suite at site as per revised drawing is accepted. | Materials to Take care to send the latest Rev of drawing to supplier End in time to avoid rework at site. | ESG Pragasam | Materials |  | Approved
14 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Invenio Engineering | Transition duct item no. FDA22A, FDA22B, FDA22C & FDA22D plate's stiffener welded at inside face of duct. Because of this, orienttion of duct got changed. | Stiffener is wrongly welded. Due to this the duct orientation will be change. | As per site proposal, all stiffeners shall be cut and re-weld with as per drawing is accepted. | Vendor inspection to be taken care in future. | ESG Pragasam | Vendor Supply & Inspection |  | Ganesh Pandi
15 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | VAISHNAV ENGINEERING | Expansion bellow of Pneumatic spreader cover plate item no. SPC025 is fouling with Buckstay support pipe & lugs at elevationEL+10050. Photos attached. | Expansion bellow of Pneumatic spreader cover plate item no. SPC025 is fouling with Buckstay support pipe & lugs at elevationEL+10050. | Kindly cut the lug plate to avoid the fouling. Reduce rod length and lug width to suit welding of bellow plate | Whenever making the seal box, that time shall be interfacing with buck stay lug locations. | ESG Pragasam | Mechanical Engg | Fouling Problem | Approved
16 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Jaydeep Engineers | The size of hole provided on SA nozzle cover plates (Item no. SPC014,015,016&017 of drawing no. JB0998-50130100-053-0002) found 64mm(ID). But the size of SA nozzle SS pipe found OD75mm (DN65). Because of this, SA nozzle pipes are not inserting in cover plate holes. | The size of SA nozzle hole on cover plate is not match with SA nozzle size. | The size of hole on cover plates have to be enlarged to match with SA nozzle size (ie. 75mm). | To be taken care in future. | ESG Pragasam | Mechanical Engg | Detail Mismatch | Approved
17 | JB0998 | SEDL.MOHALI-GOKUL MAULI SUGARS | Spring Supports Mfg. Co. | Down comer piping support Node no. 165 (RHS side) is obstracting in walkways at elevation +8400. | Down comer piping support Node no. 165 (RHS side) is obstructing in walkways at elevation +8400. | We have modified the support arrangement and shall be extand the platform as per attached SMD drawing (Drg. No.: JB0998-50100100-SMD-0001). and the additional platform material shall be arrange by site. | FInal Spring hanger GA is required before releasing the pipe supports. | ESG Pragasam | Mechanical Engg | Fouling Problem | Approved
1 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | VIJAY I.PATEL | As per contract and civil drawing, excavated soil is not to be backfilled but at site excavated soil is used for backfilling. Also backfilling is done in single step without compaction. | Erection Mistake |  |  |  | Construction
2 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Profile Engineers | IN COLUMN NO. C5 BOTTOM SEGMENT FOUND TWISTED APPROX. 10 MM. ALSO NEAR BASE PLATE COLUMN FOUND DENTED WITH 10 TO 12 MM DUE TO MISHANDLING AT SHOP. |  | Enlarge the hole |  | Sunil Kumar Gupta | Others |  | Approved
3 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | VIJAY I.PATEL | Crusher house north side columns will foul with Existing ETP plant pipe rack structure. | Crusher house north side columns will foul with Existing ETP plant pipe rack structure. As per plot plan drawing crusher house not fouling with pipe rack. | 1.Crusher house cloumn no CH1 1, CH1 2 & CH1 3 to be shifted 500mm towards tunnel side or south side to avoid fouling with existing ETP pipe rack structure. 2.Crusher house size has been revised 10500 x 10000 instead of 11000 x 10000. Revised drawing will be sent to site | We ask customer to be provide correct data and drawing. | ESG Pragasam | Client |  | Approved
4 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | SP ENGG-CORP PVT. LTD. | MCC building inside Plinth beam ( between grids A1'-B1', A2-B2) level are shown EL -0.300mm from FFL whereas in the same location Cable trenches are passing. ( cable trench depth is EL -1500mm from FFL ) If we cast these plinth beams then we can not construct our cable trench or crossing of these beams inside the trench may reduce or disturb the cabling. | Civil drawings not refered for trench layout | Plinth beam to be cast with inserting 4 nos 150mm dia pipes for running cables | Civil drawings to be referred | N.K. Goyal | Structure | Detail Mismatch
5 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Swastik Enterprises | DRILLING IN ESP CASING COLUMN 1 & COLUMN 2 FOUND WITH DIFFERENCE OF 50 MM. i.e. REQ. 1900 OBS. 1850 AND REQ. 1850 OBS. 1900. | ESP
6 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Swastik Enterprises | DRAWINGS OF SIDE WALL PANEL ASSEMBLY AND CASING COLUMNS DO NOT HAVE MATCHING HOLES FOR ERECTION. | ESP
7 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Profile Engineers | Top segment of column D-4 is having twist of 25 mm. It can not be used in as such condition. | Vendor & Inspection mistake | Rectified at site |  |  | Vendor Supply & Inspection
8 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Fabwell Engineering Enterprises | BEAM NO. 10B027 SUPPLIED OF SIZE ISMB 200 AS PER R00 BUT AS PER R01 THIS BEAM SHALL BE ISMB400 | Due to Late Revision of Drawing - Material Dispatched on 18.03.17 Rev dated - 06.03.17 but drawing not submitted to supplier . | New beams to be purchased at site | Revision to be done considering the fabrication statues in mind | Sunil Kumar Gupta | Structure | Late Revision | Approved
9 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Fabwell Engineering Enterprises | BEAM mark no. 10B037 found of ISMB300 AS PER R00 but as per R01 It shall be of ISMB500 | Due to Late Revision of Drawing - Material Dispatched on 18.03.17 Rev dated - 06.03.17 but drawing not submitted to supplier . | New beam to be purchased at site | drawing to be revised keeping frabrication statues in mind | Sunil Kumar Gupta | Structure | Late Revision | Approved
10 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Fabwell Engineering Enterprises | Beam no. 13B068 supplied of size ISMB500 as per R00 but as per R03 it is box of ISMC300. | Due to Late Revision of Drawing - Material Dispatched on 18.03.17 Rev dated - 06.03.17 but drawing not submitted to supplier . | Rectified at site | Revision to be done keeping fabrication statues in mind | Sunil Kumar Gupta | Structure | Late Revision | Approved
11 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Fabwell Engineering Enterprises | Beam item code 13B063 (ISMC250 Box) supplied in two parts. The larger part is having twist of 22 mm. | Vendor & inspection mistake | Rectified at site |  |  | Vendor Supply & Inspection
12 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Profile Engineers | Economiser support beam 5PG004 dimension discrepancy observed in the drawing . The conomiser support beams dimesnions are shown in the drawing 595 mm from the Column "E",in the same drw the plan view shows as(Rev 02) (495 mm) . Also, please see the drawing detail view "E-E". and in the casing drawing JB0999-50110106-036-0001/R.00 ,(Elevation viewed from RHS of the boiler ) the distance from E colum centre , it is shown as "495mm " which one is the correct distance? | Mismatch in the dimensions in Plan and sectional detail | The correct dimension is 495 mm as per revised Plan view. | The drawings to be checked properly matching plan and elevations | Sunil Kumar Gupta | Structure | Drawing Mistake | Approved
13 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Fabwell Engineering Enterprises | As per rev.03 drawing length of the Beam 13B034 (02 nos)has to be 3920mm, but in actual received at site as 3720mm . (which is as per the old revision), | Material Dispatched by 18.03.17 - R0. Latest Rev not Received by Supplier . R1- dated - 08.03.17 & latest Rev is Rev 3. Late Rev | Work to be done as per latest Rev . | Projects / Materials should ensure the latest rev should be send in time to supplier else acknowledge to be provide to site in advance . |  | Structure | Late Revision
14 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Flash Point | ID of 'Tee' at joint SJ10 found short by 6 mm. This can not be adjusted by grinding as thickness is as per Sch. 40 only. Also at free end edge is flattened for a length of 100 mm approx. due to manufacturing defect. | Higher Sch Fitting Send by Supplier. | Site recomendation is accepted | Taken up with Supplier and inspectors for their feedback. | ESG Pragasam | Vendor Mistake |  | Approved
15 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | STEELFAB ENGINEERING | As per drawing in roof panel FRP005 & 006, cleats of buckstay are having only 10 mm clearance for buckstay plate 10 & 12 thk. Due to less clearance plates can not be fitted. | Second and third buckstay beam top and bottom plate thickness has been increased (From10 mm to 12 mm) due to load distrubution at the time buck stay detailing same not updated in roof waer wall drawings. | Engineer shall be concider all factors of loading distrubution on roof panel in the stage of preparing water wall drawings itself. | 26 no.of cleats are cut and rewelded with pads after grinding the gap (From 10mm to 12mm). | ESG Pragasam | Mechanical Engg | Drawing Mistake | approved
16 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Dorman Engineering Pvt. Ltd. | As per drawing cleats of all beams are to be welded on three sides with connecting members but contractor is doing only vertical welding. Almost 80% structure is completed but contractor has shown no intention of doing balance work. | It is a punchlist point | Welding to be done. |  |  | Not a SAR
17 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | ATV PROJECTS INDIA LTD | DURING CLEANING OF SAFETY VALVE NOZZLE N1 & N2 OF STEAM DRUM LAMINATION FOUND AT PREPARED EDGE AT A THICKNESS OF 8-10 MM FROM OUTSIDE. AFTER GRINDING OF 10 MM HEIGHT ALSO SAME INDICATION OBSERVED. THERE AFTER WE CHECKED BOTH NOZZLES WITH 'D' METER AND FOUND THE PROBLEM PERSISTENT UPTO 25-30 MM LENGTH. | Lamination Observed in Forged Stubs - Raw Material Defect . Inspection Missout | Site recomendation is accepted and same cutoff length shall be take care in Safety valve exhaust piping. Rectification procedure provided | Taken up with Supplier and Lloyds for future action. Also, bevel edge DPT to be seen after hydro blank cutting by the inspector. | ESG Pragasam | Vendor Supply & Inspection |  | Llyods
18 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Swastik Enterprises | Size of opening in ESP Hopper is 610 mm dia but supplied doors are of 810 dia size. | Wrong supply | Opening enlarge according to door size |  |  | Vendor Mistake |  | ESP
19 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Mrudul Industries | Pipe support of Attemperator piping Node 65, 8" trunion pipe is fouling with main steam line(Almost Touching).
20 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Mrudul Industries | Riser support structure for pipe supports is fouling with main steam line.
21 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | Flash Point | As per drawing JB0999-50090100-SMD-001-REV-0 modification was sugested in main steam line. we modified the field joint but can not provide part no 101 due unavailability of material.
22 | JB0999 | UPL LTD, JHAGADIA, GUJRAT | ISGEC HEAVY ENGINEERING LTD. (YNR) | Guide plate arrestor required 10 mm dia U rod for superheater coils but due to unavailability of material 5 mm dia rod of refractory lugs provided after bending at site.
1 | JB1000 | The Seksaria Biswan Sugar Fact | Riddhi Siddhi Industries | During preassembly of ESP columns we found thickness of base plate of column is 28mm but as per drawing it should be 32mm.Length of column is maintained as per drawing.Number of columns is 10 nos
2 | JB1000 | The Seksaria Biswan Sugar Fact | Riddhi Siddhi Industries | Client drain slury waste in storage yard area also poorly handled material without any information because of this mud setteled on material.Material bracing,casing columns
3 | JB1000 | The Seksaria Biswan Sugar Fact | Bhilwara Febpro Pvt. Ltd. | 1) Tie beam 09B011 length found 4830mm but as per drawing length is 5826mm 2) Tie Beam 33B014 as per drawing ISMC 250 chanel is required but receieved ISMB 250 beam
4 | JB1000 | The Seksaria Biswan Sugar Fact | Bhilwara Engineering Service & | Boiler 2 nos tie beams & grating used as a temporary structure as shown in attached photos. Tie beam 05B002 also used as a bed material.
5 | JB1000 | The Seksaria Biswan Sugar Fact | Riddhi Siddhi Industries | During preassembly of esp casings we found panel ESW008 & ESW012 stiffner angle notch not done as per drawing.ESW012 stiffner angle notch done as per beam but actually notch to be done as per chanel. ESW008 notch not done.
6 | JB1000 | The Seksaria Biswan Sugar Fact | ISGEC HEAVY ENGG. LTD. - BAWAL | During ground assembly of LSP water wall panel we found 1) length of LSP002 is 10892mm instead of 10900mm as per drawing.Ground assembely of LSP003 LSP004,LSP005,LSP006,LSP007, LSP008 is completed. 2) Water wall bottom header height from panel tubes is 279mm instead of 284mm. 3) LSP002 bottom buckstay elevation found +5mm deviation from required dimension. | Fabrication Mistake | 1. 8 mm short in LSP002 panel can be adjusted in tube field joints between LSP001 & LSP003 & stoker sealing (as confirmed by Stoker group). 2. 5 mm. deviation in header offset distance also can be adjusted in the stoker sealing. 3. 5 mm. deviation in buckstay lug location in LSP002 panel will adjust at site as per your proposed solution | Quality has to ensure the dimensions before dispatch the components | K.V.Anguraju | Vendor Supply & Inspection | Supply not as per drawing | Approved.
7 | JB1000 | The Seksaria Biswan Sugar Fact | Bhilwara Febpro Pvt. Ltd. | 1) During erection we found Platform members lengths not as per drawing.Materail send as per bill of material but material length is differ in detail drawing. 22BT004,22BT005,22BT006,22BT007,22B094,22B098,22B061,22B062 25BT03,25BT04,25BT005,25BT008,25B066,25B067,25B068,25B089,25B090,25B091 28BT01,28BT03,28BT02,28BT06,28BT028,28BT029,28BT037,28BT038 2)Boiler left side structure already erected without rectification. Right side structure erection balance. 3) Grating fouls short in left side as platform member length not as per drawing.
8 | JB1000 | The Seksaria Biswan Sugar Fact | KSB PUMPS LTD. | During foundation inspection of boiler feed pump we found elevation is EL +170mm from zero level.As per drawing required elevation is EL + 250mm.So observed elevation difference is 80mm and grouting gap becomes 130mm.
9 | JB1000 | The Seksaria Biswan Sugar Fact | Riddhi Siddhi Industries | .ESP material Gusset plate with hollow section EIPS10,EIPS11 not supply as per drawing.As per drawing hollow section should be welded with gusset plate at shop.But gusset plate supply without hollow section .
10 | JB1000 | The Seksaria Biswan Sugar Fact | Bhilai Engineering Works | Boiler platform at elevation 25675 mm width of platform structure is 1000 mm as per drawing but actually we found width of structure is 1140mm.Because of this grating width becomes short.
11 | JB1000 | The Seksaria Biswan Sugar Fact | ISGEC HEAVY ENGG. LTD. - BAWAL | During super heater coil shifting at site from yard to boiler area observed 4 nos coils bends.one primary super heater coil,two Intermidiate super heater coil and one secondry super heater coil.Two Intermidiate coils already fit-up in bend condition.