## JB1015 10.1
Element |  | Level | Initial Total Budget | Revised Intital Total Budget | Addition/Reduction Due to Client Till Date | Addition/Reduction Due to Internal Transfer Till Date | Total Budget | Available Amount For Indenting | Available Amount For Purchase Order | Soft Allocation | Exhausted in Modified PO's | Exhausted | Distributed Amount | Undstributed Amount | Transfer To CTOH | Transfer of Savings To Contigency - S | Savings Transferred Amount | Transfered From Element |  | Reason Code |  | Revised/Trf Amount | Total To Be Transferred | Transferred From Contingency | Transferred From Contingency-S | Transferred From Warranty | Transferred From CTOH | Transfer From Freight | Transfer From P&F | Transfer From TPC | Reason For Partial Revise | Addition/Reduction Due to Client | Addition/Reduction Due to Internal Transfer | Remarks
1 | Total Budget | L1 | 72134529.97 | 0 | 0 | 0 | 86854529.97 | 10239348.57 | 10623548.57 | 384200 | 0 | 76230981.4 | 86854529.97 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50000000 | BOILER | L2 | 66984529.97 | 0 | 0 | 0 | 83159529.97 | 9325013.14 | 9709213.14 | 384200 | 0 | 73450316.83 | 83159529.97 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50010000 | Drum | L3 | 1468969.03 | 0 | 0 | 0 | 1468969.03 | 160667.25 | 160667.25 | 0 | 0 | 1308301.78 | 1468969.03 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50010100 | Steam Drum and Mud drum with internals and attachm | L4 | 1468969.03 | 0 | 0 | 0 | 1468969.03 | 160667.25 | 160667.25 | 0 | 0 | 1308301.78 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50020000 | Boiler Water Wall and Circulating System Component | L3 | 6238314 | 0 | 0 | 0 | 6238314 | 148313 | 148313 | 0 | 0 | 6090001 | 6238314 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50020500 | Evaporator wing wall assembly | L4 | 6238314 | 0 | 0 | 0 | 6238314 | 148313 | 148313 | 0 | 0 | 6090001 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50030000 | Superheater Assembly | L3 | 12158393.11 | 0 | 0 | 0 | 12158393.11 | 391.61 | 391.61 | 0 | 0 | 12158001.5 | 12158393.11 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50030100 | Convection super heater Assembly(Primary-Secondary | L4 | 12158393.11 | 0 | 0 | 0 | 12158393.11 | 391.61 | 391.61 | 0 | 0 | 12158001.5 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50040000 | Forced Flow Assembly | L3 | 16076785.63 | 0 | 0 | 0 | 16076785.63 | 1533782.63 | 1533782.63 | 0 | 0 | 14543003 | 16076785.63 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50040100 | Forced Flow Elements assembly | L4 | 10176785.63 | 0 | 0 | 0 | 11676785.63 | 234782.63 | 234782.63 | 0 | 0 | 11442003 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50040500 | Header Support assembly | L4 | 5900000 | 0 | 0 | 0 | 4400000 | 1299000 | 1299000 | 0 | 0 | 3101000 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060000 | Boiler Supporting Steelworks and canopy | L3 | 3875318.2 | 0 | 0 | 0 | 3675318.2 | 458321.39 | 481321.39 | 23000 | 0 | 3193996.81 | 3675318.2 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060100 | Columns | L4 | 3641220 | 0 | 0 | 0 | 488893 | 0.75 | 0.75 | 0 | 0 | 488892.25 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060200 | Beams | L4 | 0 | 0 | 0 | 0 | 2350593 | 8205.58 | 8205.58 | 0 | 0 | 2342387.42 | 0 | 0 | 0 | No | 0 | 50060600 | Structure for Canopy | 1 | L4/L5 Sanction Transfer | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060300 | Bracing | L4 | 0 | 0 | 0 | 0 | 270832 | 0.24 | 0.24 | 0 | 0 | 270831.76 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060400 | Drum lifting structure | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060600 | Structure for Canopy | L4 | 0 | 0 | 0 | 0 | 542000 | 450114.62 | 450114.62 | 0 | 0 | 91885.38 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060700 | Sheeting for Canopy | L4 | 234098.2 | 0 | 0 | 0 | 13000.2 | 0.2 | 13000.2 | 13000 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060800 | Fixtures for Canopy | L4 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070000 | Gallery & Ladder | L3 | 1422800 | 0 | 0 | 0 | 1422800 | 12542.61 | 12542.61 | 0 | 0 | 1410257.39 | 1422800 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070100 | Chequred plates | L4 | 1026000 | 0 | 0 | 0 | 9584 | 9584 | 9584 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070200 | Gratings | L4 | 0 | 0 | 0 | 0 | 791900 | 2957.9 | 2957.9 | 0 | 0 | 788942.1 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070300 | Ladders | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070400 | Staircases/Stair Tread | L4 | 0 | 0 | 0 | 0 | 171942 | 0.04 | 0.04 | 0 | 0 | 171941.96 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070500 | Hand Rails | L4 | 396800 | 0 | 0 | 0 | 449374 | 0.67 | 0.67 | 0 | 0 | 449373.33 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50080000 | Ducting- Expansion Joint -Dampers and Supports | L3 | 5600000 | 0 | 0 | 0 | 8224000 | 1527351.49 | 1536551.49 | 9200 | 0 | 6687448.51 | 6730000 | 1494000 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50080100 | FD air ducting assembly with supports | L4 | 5600000 | 0 | 0 | 0 | 330420 | -9199 | 1 | 9200 | 0 | 330419 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50080400 | Flue Gas Ducting assembly with supports | L4 | 0 | 0 | 0 | 0 | 6399580 | 42550.49 | 42550.49 | 0 | 0 | 6357029.51 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090000 | Pipework | L3 | 3100750 | 0 | 0 | 0 | 3500750 | 676773.44 | 676773.44 | 0 | 0 | 2823976.56 | 3500750 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090100 | Integral Pipework | L4 | 2048750 | 0 | 0 | 0 | 2023750 | 151992 | 151992 | 0 | 0 | 1871758 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090200 | Attemperator | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090201 | Fixed orifice attemperators for Boiler Integral | L5 | 0 | 0 | 0 | 0 | 25000 | 1000 | 1000 | 0 | 0 | 24000 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090400 | Boiler house Pipe works | L4 | 1052000 | 0 | 0 | 0 | 851000 | 204897.44 | 204897.44 | 0 | 0 | 646102.56 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090401 | 50 NB and above Boiler House Pipework | L5 | 0 | 0 | 0 | 0 | 1000 | 999 | 999 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090402 | 40 NB and above Boiler House Pipework | L5 | 0 | 0 | 0 | 0 | 600000 | 317885 | 317885 | 0 | 0 | 282115 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090500 | Cooling water pipe work | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090600 | Instrument air pipework | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100000 | Pipe Supports | L3 | 811500 | 0 | 0 | 0 | 811500 | 248059.08 | 348059.08 | 100000 | 0 | 463440.92 | 811500 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100100 | Structure & Pipe Support accessories for integral | L4 | 599000 | 0 | 0 | 0 | 289000 | 174392.08 | 174392.08 | 0 | 0 | 114607.92 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100200 | Spring Hangers for integral piping | L4 | 212500 | 0 | 0 | 0 | 212500 | 38581 | 138581 | 100000 | 0 | 73919 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100300 | Structure & Pipe Support accessories for Boiler ho | L4 | 0 | 0 | 0 | 0 | 210000 | 3786 | 3786 | 0 | 0 | 206214 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100400 | Spring Hangers forBoiler house piping and other pi | L4 | 0 | 0 | 0 | 0 | 100000 | 31300 | 31300 | 0 | 0 | 68700 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50110000 | Casing | L3 | 5604000 | 0 | 0 | 0 | 17000000 | 2272645 | 2272645 | 0 | 0 | 14727355 | 17000000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50110100 | Boiler Casings | L4 | 5604000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50110101 | Front Boiler Casing | L5 | 0 | 0 | 0 | 0 | 17000000 | 2272645 | 2272645 | 0 | 0 | 14727355 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50130000 | Seal Boxes and Sealing Arrangements | L3 | 132500 | 0 | 0 | 0 | 132500 | 8413.98 | 8413.98 | 0 | 0 | 124086.02 | 132500 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50130100 | Seal plate and cover plates | L4 | 132500 | 0 | 0 | 0 | 132500 | 8413.98 | 8413.98 | 0 | 0 | 124086.02 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50130200 | Furnace bottom sealing assembly | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50140000 | Refractory arrangement | L3 | 428800 | 0 | 0 | 0 | 428800 | 428800 | 428800 | 0 | 0 | 0 | 428800 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50140100 | Refractory materials | L4 | 128800 | 0 | 0 | 0 | 128800 | 128800 | 128800 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50140200 | Refractory Applications | L4 | 300000 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50150000 | Concrete insert materials | L3 | 224000 | 0 | 0 | 0 | 224000 | 180355.36 | 180355.36 | 0 | 0 | 43644.64 | 224000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50150200 | Foundation bolts and shim plates for Boiler | L4 | 224000 | 0 | 0 | 0 | 224000 | 180355.36 | 180355.36 | 0 | 0 | 43644.64 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50150400 | Foundation bolts and shim plates for Auxiliary equ | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50160000 | Fasteners and gaskets | L3 | 60000 | 0 | 0 | 0 | 60000 | 51409.74 | 51409.74 | 0 | 0 | 8590.26 | 60000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50160200 | Fasteners | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50160202 | Fasteners for Integral piping | L5 | 0 | 0 | 0 | 0 | 13000 | 9818.6 | 9818.6 | 0 | 0 | 3181.4 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50160300 | Gaskets | L4 | 60000 | 0 | 0 | 0 | 47000 | 41591.14 | 41591.14 | 0 | 0 | 5408.86 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50170000 | Boiler Rough Mountings | L3 | 240000 | 0 | 0 | 0 | 240000 | 121141 | 121141 | 0 | 0 | 118859 | 240000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50170100 | Standard Castings doors and fittings | L4 | 240000 | 0 | 0 | 0 | 240000 | 121141 | 121141 | 0 | 0 | 118859 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50210000 | Hoppers | L3 | 896900 | 0 | 0 | 0 | 896900 | 832900 | 832900 | 0 | 0 | 64000 | 896900 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50210100 | Front Ash hopper / Bed Ash Hopper | L4 | 896900 | 0 | 0 | 0 | 896900 | 832900 | 832900 | 0 | 0 | 64000 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50350000 | Insulation Material/Cladding | L3 | 391000 | 0 | 0 | 0 | 391000 | 151000 | 391000 | 240000 | 0 | 0 | 391000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50350200 | Cladding | L4 | 391000 | 0 | 0 | 0 | 391000 | 151000 | 391000 | 240000 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50460000 | Pollution Control System | L3 | 7599000 | 0 | 0 | 0 | 9599000 | 210160.56 | 210160.56 | 0 | 0 | 9388839.44 | 9599000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50460500 | Low efficiency Dust collector | L4 | 7599000 | 0 | 0 | 0 | 9599000 | 210160.56 | 210160.56 | 0 | 0 | 9388839.44 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50500000 | Boiler Mounting & Fitting | L3 | 440000 | 0 | 0 | 0 | 440000 | 228000 | 228000 | 0 | 0 | 212000 | 440000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50500200 | Silencer | L4 | 420000 | 0 | 0 | 0 | 420000 | 208000 | 208000 | 0 | 0 | 212000 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50501200 | Steam traps | L4 | 20000 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50530000 | Maintenance Tool | L3 | 50000 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50550000 | Spare | L3 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50550100 | Commissioning Spare | L4 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50570000 | Miscellaneous Items | L3 | 115500 | 0 | 0 | 0 | 115500 | 18985 | 30985 | 12000 | 0 | 84515 | 115500 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50570800 | Chemicals | L4 | 70500 | 0 | 0 | 0 | 18500 | 18500 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50571100 | Boiler Name plates | L4 | 45000 | 0 | 0 | 0 | 97000 | 485 | 12485 | 12000 | 0 | 84515 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99000000 | Common & Miscellaneous Cost Elements | L2 | 5150000 | 0 | 0 | 0 | 3695000 | 914335.43 | 914335.43 | 0 | 0 | 2780664.57 | 3695000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99040000 | Packing & Forwarding | L3 | 900000 | 0 | 0 | 0 | 500000 | 30744.88 | 30744.88 | 0 | 0 | 469255.12 | 500000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99040100 | Packing and Forwarding | L4 | 900000 | 0 | 0 | 0 | 500000 | 30744.88 | 30744.88 | 0 | 0 | 469255.12 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99050000 | Freight | L3 | 2100000 | 0 | 0 | 0 | 2100000 | 8083 | 8083 | 0 | 0 | 2091917 | 2100000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99050500 | Inland Freight | L4 | 2100000 | 0 | 0 | 0 | 2100000 | 8083 | 8083 | 0 | 0 | 2091917 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99080000 | Project Overheads / Sundry Costs | L3 | 300000 | 0 | 0 | 0 | 300000 | 80507.55 | 80507.55 | 0 | 0 | 219492.45 | 300000 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99080300 | Inspection Charges | L4 | 150000 | 0 | 0 | 0 | 100000 | 19291 | 19291 | 0 | 0 | 80709 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99080600 | Bank Charge(Supply Project) | L4 | 150000 | 0 | 0 | 0 | 150000 | 61216.55 | 61216.55 | 0 | 0 | 88783.45 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99081000 | Consultancy Charges | L4 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99100000 | Contingency | L3 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99110000 | Warranty | L3 | 750000 | 0 | 0 | 0 | 750000 | 750000 | 750000 | 0 | 0 | 0 | 0 | 750000 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99180000 | Contingency-S | L3 | 0 | 0 | 0 | 0 | 45000 | 45000 | 45000 | 0 | 0 | 0 | 0 | 45000 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99250000 | Travel | L3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99250100 | Travel - Others | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0

## JB1015.10.2
Element |  | Level | Initial Total Budget | Revised Intital Total Budget | Addition/Reduction Due to Client Till Date | Addition/Reduction Due to Internal Transfer Till Date | Total Budget | Available Amount For Indenting | Available Amount For Purchase Order | Soft Allocation | Exhausted in Modified PO's | Exhausted | Distributed Amount | Undstributed Amount | Transfer To CTOH | Transfer of Savings To Contigency - S | Savings Transferred Amount | Transfered From Element | Reason Code | Revised/Trf Amount | Total To Be Transferred | Transferred From Contingency | Transferred From Contingency-S | Transferred From Warranty | Transferred From CTOH | Transfer From Freight | Transfer From P&F | Transfer From TPC | Reason For Partial Revise |  | Addition/Reduction Due to Client | Addition/Reduction Due to Internal Transfer | Remarks
1 | Total Budget | L1 | 72134529.97 | 0 | 0 | 0 | 86854529.97 | 10239348.57 | 10623548.57 | 384200 | 0 | 76230981.4 | 86854529.97 | 86854529.97 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50000000 | BOILER | L2 | 66984529.97 | 0 | 0 | 0 | 83259529.97 | 9425013.14 | 9809213.14 | 384200 | 0 | 73450316.83 | 83259529.97 | 83159529.97 | 100000 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50010000 | Drum | L3 | 1468969.03 | 0 | 0 | 0 | 1568969.03 | 260667.25 | 260667.25 | 0 | 0 | 1308301.78 | 1468969.03 | 100000 | 0 | No | 0 |  |  | 0 | 100000 | 0 | 35000 | 65000 | 0 | 0 | 0 | 0 | C01 | Estimation Missout/detailed de | 0 | 0
50010100 | Steam Drum and Mud drum with internals and attachm | L4 | 1468969.03 | 0 | 0 | 0 | 1468969.03 | 160667.25 | 160667.25 | 0 | 0 | 1308301.78 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50020000 | Boiler Water Wall and Circulating System Component | L3 | 6238314 | 0 | 0 | 0 | 6238314 | 148313 | 148313 | 0 | 0 | 6090001 | 6238314 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50020500 | Evaporator wing wall assembly | L4 | 6238314 | 0 | 0 | 0 | 6238314 | 148313 | 148313 | 0 | 0 | 6090001 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50030000 | Superheater Assembly | L3 | 12158393.11 | 0 | 0 | 0 | 12158393.11 | 391.61 | 391.61 | 0 | 0 | 12158001.5 | 12158393.11 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50030100 | Convection super heater Assembly(Primary-Secondary | L4 | 12158393.11 | 0 | 0 | 0 | 12158393.11 | 391.61 | 391.61 | 0 | 0 | 12158001.5 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50040000 | Forced Flow Assembly | L3 | 16076785.63 | 0 | 0 | 0 | 16076785.63 | 1533782.63 | 1533782.63 | 0 | 0 | 14543003 | 16076785.63 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50040100 | Forced Flow Elements assembly | L4 | 10176785.63 | 0 | 0 | 0 | 11676785.63 | 234782.63 | 234782.63 | 0 | 0 | 11442003 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50040500 | Header Support assembly | L4 | 5900000 | 0 | 0 | 0 | 4400000 | 1299000 | 1299000 | 0 | 0 | 3101000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060000 | Boiler Supporting Steelworks and canopy | L3 | 3875318.2 | 0 | 0 | 0 | 3675318.2 | 458321.39 | 481321.39 | 23000 | 0 | 3193996.81 | 3675318.2 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060100 | Columns | L4 | 3641220 | 0 | 0 | 0 | 488893 | 0.75 | 0.75 | 0 | 0 | 488892.25 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060200 | Beams | L4 | 0 | 0 | 0 | 0 | 2350593 | 8205.58 | 8205.58 | 0 | 0 | 2342387.42 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060300 | Bracing | L4 | 0 | 0 | 0 | 0 | 270832 | 0.24 | 0.24 | 0 | 0 | 270831.76 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060400 | Drum lifting structure | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060600 | Structure for Canopy | L4 | 0 | 0 | 0 | 0 | 542000 | 450114.62 | 450114.62 | 0 | 0 | 91885.38 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060700 | Sheeting for Canopy | L4 | 234098.2 | 0 | 0 | 0 | 13000.2 | 0.2 | 13000.2 | 13000 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060800 | Fixtures for Canopy | L4 | 0 | 0 | 0 | 0 | 10000 | 0 | 10000 | 10000 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070000 | Gallery & Ladder | L3 | 1422800 | 0 | 0 | 0 | 1422800 | 12542.61 | 12542.61 | 0 | 0 | 1410257.39 | 1422800 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070100 | Chequred plates | L4 | 1026000 | 0 | 0 | 0 | 9584 | 9584 | 9584 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070200 | Gratings | L4 | 0 | 0 | 0 | 0 | 791900 | 2957.9 | 2957.9 | 0 | 0 | 788942.1 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070300 | Ladders | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070400 | Staircases/Stair Tread | L4 | 0 | 0 | 0 | 0 | 171942 | 0.04 | 0.04 | 0 | 0 | 171941.96 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070500 | Hand Rails | L4 | 396800 | 0 | 0 | 0 | 449374 | 0.67 | 0.67 | 0 | 0 | 449373.33 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50080000 | Ducting- Expansion Joint -Dampers and Supports | L3 | 5600000 | 0 | 0 | 0 | 8224000 | 1527351.49 | 1536551.49 | 9200 | 0 | 6687448.51 | 6730000 | 1494000 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50080100 | FD air ducting assembly with supports | L4 | 5600000 | 0 | 0 | 0 | 330420 | -9199 | 1 | 9200 | 0 | 330419 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50080400 | Flue Gas Ducting assembly with supports | L4 | 0 | 0 | 0 | 0 | 6399580 | 42550.49 | 42550.49 | 0 | 0 | 6357029.51 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090000 | Pipework | L3 | 3100750 | 0 | 0 | 0 | 3500750 | 676773.44 | 676773.44 | 0 | 0 | 2823976.56 | 3500750 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090100 | Integral Pipework | L4 | 2048750 | 0 | 0 | 0 | 2023750 | 151992 | 151992 | 0 | 0 | 1871758 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090200 | Attemperator | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090201 | Fixed orifice attemperators for Boiler Integral | L5 | 0 | 0 | 0 | 0 | 25000 | 1000 | 1000 | 0 | 0 | 24000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090400 | Boiler house Pipe works | L4 | 1052000 | 0 | 0 | 0 | 851000 | 204897.44 | 204897.44 | 0 | 0 | 646102.56 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090401 | 50 NB and above Boiler House Pipework | L5 | 0 | 0 | 0 | 0 | 1000 | 999 | 999 | 0 | 0 | 1 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090402 | 40 NB and above Boiler House Pipework | L5 | 0 | 0 | 0 | 0 | 600000 | 317885 | 317885 | 0 | 0 | 282115 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090500 | Cooling water pipe work | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090600 | Instrument air pipework | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100000 | Pipe Supports | L3 | 811500 | 0 | 0 | 0 | 811500 | 248059.08 | 348059.08 | 100000 | 0 | 463440.92 | 811500 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100100 | Structure & Pipe Support accessories for integral | L4 | 599000 | 0 | 0 | 0 | 289000 | 174392.08 | 174392.08 | 0 | 0 | 114607.92 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100200 | Spring Hangers for integral piping | L4 | 212500 | 0 | 0 | 0 | 212500 | 38581 | 138581 | 100000 | 0 | 73919 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100300 | Structure & Pipe Support accessories for Boiler ho | L4 | 0 | 0 | 0 | 0 | 210000 | 3786 | 3786 | 0 | 0 | 206214 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100400 | Spring Hangers forBoiler house piping and other pi | L4 | 0 | 0 | 0 | 0 | 100000 | 31300 | 31300 | 0 | 0 | 68700 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50110000 | Casing | L3 | 5604000 | 0 | 0 | 0 | 17000000 | 2272645 | 2272645 | 0 | 0 | 14727355 | 17000000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50110100 | Boiler Casings | L4 | 5604000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50110101 | Front Boiler Casing | L5 | 0 | 0 | 0 | 0 | 17000000 | 2272645 | 2272645 | 0 | 0 | 14727355 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50130000 | Seal Boxes and Sealing Arrangements | L3 | 132500 | 0 | 0 | 0 | 132500 | 8413.98 | 8413.98 | 0 | 0 | 124086.02 | 132500 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50130100 | Seal plate and cover plates | L4 | 132500 | 0 | 0 | 0 | 132500 | 8413.98 | 8413.98 | 0 | 0 | 124086.02 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50130200 | Furnace bottom sealing assembly | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50140000 | Refractory arrangement | L3 | 428800 | 0 | 0 | 0 | 428800 | 428800 | 428800 | 0 | 0 | 0 | 428800 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50140100 | Refractory materials | L4 | 128800 | 0 | 0 | 0 | 128800 | 128800 | 128800 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50140200 | Refractory Applications | L4 | 300000 | 0 | 0 | 0 | 300000 | 300000 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50150000 | Concrete insert materials | L3 | 224000 | 0 | 0 | 0 | 224000 | 180355.36 | 180355.36 | 0 | 0 | 43644.64 | 224000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50150200 | Foundation bolts and shim plates for Boiler | L4 | 224000 | 0 | 0 | 0 | 224000 | 180355.36 | 180355.36 | 0 | 0 | 43644.64 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50150400 | Foundation bolts and shim plates for Auxiliary equ | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50160000 | Fasteners and gaskets | L3 | 60000 | 0 | 0 | 0 | 60000 | 51409.74 | 51409.74 | 0 | 0 | 8590.26 | 60000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50160200 | Fasteners | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50160202 | Fasteners for Integral piping | L5 | 0 | 0 | 0 | 0 | 13000 | 9818.6 | 9818.6 | 0 | 0 | 3181.4 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50160300 | Gaskets | L4 | 60000 | 0 | 0 | 0 | 47000 | 41591.14 | 41591.14 | 0 | 0 | 5408.86 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50170000 | Boiler Rough Mountings | L3 | 240000 | 0 | 0 | 0 | 240000 | 121141 | 121141 | 0 | 0 | 118859 | 240000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50170100 | Standard Castings doors and fittings | L4 | 240000 | 0 | 0 | 0 | 240000 | 121141 | 121141 | 0 | 0 | 118859 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50210000 | Hoppers | L3 | 896900 | 0 | 0 | 0 | 896900 | 832900 | 832900 | 0 | 0 | 64000 | 896900 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50210100 | Front Ash hopper / Bed Ash Hopper | L4 | 896900 | 0 | 0 | 0 | 896900 | 832900 | 832900 | 0 | 0 | 64000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50350000 | Insulation Material/Cladding | L3 | 391000 | 0 | 0 | 0 | 391000 | 151000 | 391000 | 240000 | 0 | 0 | 391000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50350200 | Cladding | L4 | 391000 | 0 | 0 | 0 | 391000 | 151000 | 391000 | 240000 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50460000 | Pollution Control System | L3 | 7599000 | 0 | 0 | 0 | 9599000 | 210160.56 | 210160.56 | 0 | 0 | 9388839.44 | 9599000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50460500 | Low efficiency Dust collector | L4 | 7599000 | 0 | 0 | 0 | 9599000 | 210160.56 | 210160.56 | 0 | 0 | 9388839.44 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50500000 | Boiler Mounting & Fitting | L3 | 440000 | 0 | 0 | 0 | 440000 | 228000 | 228000 | 0 | 0 | 212000 | 440000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50500200 | Silencer | L4 | 420000 | 0 | 0 | 0 | 420000 | 208000 | 208000 | 0 | 0 | 212000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50501200 | Steam traps | L4 | 20000 | 0 | 0 | 0 | 20000 | 20000 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50530000 | Maintenance Tool | L3 | 50000 | 0 | 0 | 0 | 5000 | 5000 | 5000 | 0 | 0 | 0 | 0 | 5000 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50550000 | Spare | L3 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50550100 | Commissioning Spare | L4 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50570000 | Miscellaneous Items | L3 | 115500 | 0 | 0 | 0 | 115500 | 18985 | 30985 | 12000 | 0 | 84515 | 115500 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50570800 | Chemicals | L4 | 70500 | 0 | 0 | 0 | 18500 | 18500 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50571100 | Boiler Name plates | L4 | 45000 | 0 | 0 | 0 | 97000 | 485 | 12485 | 12000 | 0 | 84515 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99000000 | Common & Miscellaneous Cost Elements | L2 | 5150000 | 0 | 0 | 0 | 3595000 | 814335.43 | 814335.43 | 0 | 0 | 2780664.57 | 3595000 | 0 | 3695000 | 100000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99040000 | Packing & Forwarding | L3 | 900000 | 0 | 0 | 0 | 500000 | 30744.88 | 30744.88 | 0 | 0 | 469255.12 | 500000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99040100 | Packing and Forwarding | L4 | 900000 | 0 | 0 | 0 | 500000 | 30744.88 | 30744.88 | 0 | 0 | 469255.12 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99050000 | Freight | L3 | 2100000 | 0 | 0 | 0 | 2100000 | 8083 | 8083 | 0 | 0 | 2091917 | 2100000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99050500 | Inland Freight | L4 | 2100000 | 0 | 0 | 0 | 2100000 | 8083 | 8083 | 0 | 0 | 2091917 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99080000 | Project Overheads / Sundry Costs | L3 | 300000 | 0 | 0 | 0 | 300000 | 80507.55 | 80507.55 | 0 | 0 | 219492.45 | 300000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99080300 | Inspection Charges | L4 | 150000 | 0 | 0 | 0 | 100000 | 19291 | 19291 | 0 | 0 | 80709 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99080600 | Bank Charge(Supply Project) | L4 | 150000 | 0 | 0 | 0 | 150000 | 61216.55 | 61216.55 | 0 | 0 | 88783.45 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99081000 | Consultancy Charges | L4 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99100000 | Contingency | L3 | 1100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99110000 | Warranty | L3 | 750000 | 0 | 0 | 0 | 685000 | 685000 | 685000 | 0 | 0 | 0 | 0 | 685000 | 750000 | 65000 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99180000 | Contingency-S | L3 | 0 | 0 | 0 | 0 | 10000 | 10000 | 10000 | 0 | 0 | 0 | 0 | 10000 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99250000 | Travel | L3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99250100 | Travel - Others | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0

## JB1016 11.2
Element |  | Level | Initial Total Budget | Revised Intital Total Budget | Addition/Reduction Due to Client Till Date | Addition/Reduction Due to Internal Transfer Till Date | Total Budget | Available Amount For Indenting | Available Amount For Purchase Order | Soft Allocation | Exhausted in Modified PO's | Exhausted | Distributed Amount | Undstributed Amount | Transfer To CTOH | Transfer of Savings To Contigency - S | Savings Transferred Amount | Transfered From Element | Reason Code | Revised/Trf Amount | Total To Be Transferred | Transferred From Contingency | Transferred From Contingency-S | Transferred From Warranty | Transferred From CTOH | Transfer From Freight | Transfer From P&F | Transfer From TPC | Reason For Partial Revise | Addition/Reduction Due to Client | Addition/Reduction Due to Internal Transfer | Remarks
1 | Total Budget | L1 | 90769680.14 | 0 | 0 | 0 | 99519679.74 | 3082121.31 | 4027921.31 | 945800 | 0 | 95491758.43 | 99519679.74 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50000000 | BOILER | L2 | 80419680.14 | 0 | 0 | 0 | 90119679.74 | 611140.56 | 1556940.56 | 945800 | 0 | 88562739.18 | 90119679.74 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50010000 | Drum | L3 | 1840377.11 | 0 | 0 | 0 | 1840377.11 | 152383.9 | 152383.9 | 0 | 0 | 1687993.21 | 1840377.11 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50010100 | Steam Drum and Mud drum with internals and attachm | L4 | 1840377.11 | 0 | 0 | 0 | 1840377.11 | 152383.9 | 152383.9 | 0 | 0 | 1687993.21 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50020000 | Boiler Water Wall and Circulating System Component | L3 | 33166759.65 | 0 | 0 | 0 | 33166759.65 | 0 | 0 | 0 | 0 | 33166759.65 | 33166759.65 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50020500 | Evaporator wing wall assembly | L4 | 33166759.65 | 0 | 0 | 0 | 33166759.65 | 0 | 0 | 0 | 0 | 33166759.65 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50030000 | Superheater Assembly | L3 | 2632797.51 | 0 | 0 | 0 | 2632797.51 | 0.51 | 0.51 | 0 | 0 | 2632797 | 2632797.51 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50030100 | Convection super heater Assembly(Primary-Secondary | L4 | 2632797.51 | 0 | 0 | 0 | 2632797.51 | 0.51 | 0.51 | 0 | 0 | 2632797 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50040000 | Forced Flow Assembly | L3 | 11661562.47 | 0 | 0 | 0 | 11661562.47 | 2492.12 | 2492.12 | 0 | 0 | 11659070.35 | 11661562.47 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50040100 | Forced Flow Elements assembly | L4 | 11661562.47 | 0 | 0 | 0 | 11657903.47 | 2492.12 | 2492.12 | 0 | 0 | 11655411.35 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50040500 | Header Support assembly | L4 | 0 | 0 | 0 | 0 | 3659 | 0 | 0 | 0 | 0 | 3659 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060000 | Boiler Supporting Steelworks and canopy | L3 | 5700983.4 | 0 | 0 | 0 | 11600983 | 340057.93 | 344257.93 | 4200 | 0 | 11256725.07 | 11600983 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060100 | Columns | L4 | 5400000 | 0 | 0 | 0 | 2547825 | 3700.68 | 3700.68 | 0 | 0 | 2544124.32 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060200 | Beams | L4 | 0 | 0 | 0 | 0 | 8907057.6 | 202120.01 | 202120.01 | 0 | 0 | 8704937.59 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060300 | Bracing | L4 | 0 | 0 | 0 | 0 | 100 | 99.99 | 99.99 | 0 | 0 | 0.01 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060400 | Drum lifting structure | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060600 | Structure for Canopy | L4 | 0 | 0 | 0 | 0 | 15000 | 7336.85 | 7336.85 | 0 | 0 | 7663.15 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060700 | Sheeting for Canopy | L4 | 300983.4 | 0 | 0 | 0 | 131000.4 | 126800.4 | 131000.4 | 4200 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50060800 | Fixtures for Canopy | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070000 | Gallery & Ladder | L3 | 2916400 | 0 | 0 | 0 | 4616400 | 117225.48 | 117225.48 | 0 | 0 | 4499174.52 | 4534700 | 81700 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070100 | Chequred plates | L4 | 2084400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070200 | Gratings | L4 | 0 | 0 | 0 | 0 | 2977721 | 35435.41 | 35435.41 | 0 | 0 | 2942285.59 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070300 | Ladders | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070400 | Staircases/Stair Tread | L4 | 0 | 0 | 0 | 0 | 267240 | 0.51 | 0.51 | 0 | 0 | 267239.49 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50070500 | Hand Rails | L4 | 832000 | 0 | 0 | 0 | 1289739 | 89.56 | 89.56 | 0 | 0 | 1289649.44 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50080000 | Ducting- Expansion Joint -Dampers and Supports | L3 | 378000 | 0 | 0 | 0 | 1278000 | 49154.65 | 49154.65 | 0 | 0 | 1228845.35 | 1266305 | 11695 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50080100 | FD air ducting assembly with supports | L4 | 378000 | 0 | 0 | 0 | 585805 | 0 | 0 | 0 | 0 | 585805 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50080400 | Flue Gas Ducting assembly with supports | L4 | 0 | 0 | 0 | 0 | 680500 | 37459.65 | 37459.65 | 0 | 0 | 643040.35 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090000 | Pipework | L3 | 4419000 | 0 | 0 | 0 | 4819000 | -494783.11 | 25216.89 | 520000 | 0 | 4793783.11 | 4819000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090100 | Integral Pipework | L4 | 2585000 | 0 | 0 | 0 | 3105000 | -519674.76 | 325.24 | 520000 | 0 | 3104674.76 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090400 | Boiler house Pipe works | L4 | 1834000 | 0 | 0 | 0 | 1113000 | 54.65 | 54.65 | 0 | 0 | 1112945.35 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090401 | 50 NB and above Boiler House Pipework | L5 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090402 | 40 NB and above Boiler House Pipework | L5 | 0 | 0 | 0 | 0 | 600000 | 24837 | 24837 | 0 | 0 | 575163 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090500 | Cooling water pipe work | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50090600 | Instrument air pipework | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100000 | Pipe Supports | L3 | 1253000 | 0 | 0 | 0 | 1253000 | 30466.19 | 30466.19 | 0 | 0 | 1222533.81 | 1253000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100100 | Structure & Pipe Support accessories for integral | L4 | 896000 | 0 | 0 | 0 | 646000 | -85311.81 | -85311.81 | 0 | 0 | 731311.81 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100200 | Spring Hangers for integral piping | L4 | 357000 | 0 | 0 | 0 | 133590 | 0 | 0 | 0 | 0 | 133590 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100300 | Structure & Pipe Support accessories for Boiler ho | L4 | 0 | 0 | 0 | 0 | 397180 | 115778 | 115778 | 0 | 0 | 281402 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50100400 | Spring Hangers forBoiler house piping and other pi | L4 | 0 | 0 | 0 | 0 | 76230 | 0 | 0 | 0 | 0 | 76230 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50110000 | Casing | L3 | 5353000 | 0 | 0 | 0 | 5353000 | 0.99 | 0.99 | 0 | 0 | 5352999.01 | 5353000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50110100 | Boiler Casings | L4 | 5353000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50110101 | Front Boiler Casing | L5 | 0 | 0 | 0 | 0 | 5353000 | 0.99 | 0.99 | 0 | 0 | 5352999.01 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50130000 | Seal Boxes and Sealing Arrangements | L3 | 450500 | 0 | 0 | 0 | 450500 | 30608 | 30608 | 0 | 0 | 419892 | 450500 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50130100 | Seal plate and cover plates | L4 | 450500 | 0 | 0 | 0 | 450500 | 30608 | 30608 | 0 | 0 | 419892 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50130200 | Furnace bottom sealing assembly | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50150000 | Concrete insert materials | L3 | 392000 | 0 | 0 | 0 | 392000 | 1624.92 | 1624.92 | 0 | 0 | 390375.08 | 392000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50150200 | Foundation bolts and shim plates for Boiler | L4 | 280000 | 0 | 0 | 0 | 390376 | 0.92 | 0.92 | 0 | 0 | 390375.08 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50150400 | Foundation bolts and shim plates for Auxiliary equ | L4 | 112000 | 0 | 0 | 0 | 1624 | 1624 | 1624 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50160000 | Fasteners and gaskets | L3 | 55000 | 0 | 0 | 0 | 55000 | 14620.98 | 14620.98 | 0 | 0 | 40379.02 | 55000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50160200 | Fasteners | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50160202 | Fasteners for Integral piping | L5 | 0 | 0 | 0 | 0 | 12000 | 7952 | 7952 | 0 | 0 | 4048 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50160300 | Gaskets | L4 | 55000 | 0 | 0 | 0 | 43000 | 6668.98 | 6668.98 | 0 | 0 | 36331.02 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50170000 | Boiler Rough Mountings | L3 | 264000 | 0 | 0 | 0 | 264000 | 1 | 1 | 0 | 0 | 263999 | 264000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50170100 | Standard Castings doors and fittings | L4 | 264000 | 0 | 0 | 0 | 264000 | 1 | 1 | 0 | 0 | 263999 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50210000 | Hoppers | L3 | 577000 | 0 | 0 | 0 | 1377000 | 79110 | 79110 | 0 | 0 | 1297890 | 1363281 | 13719 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50210100 | Front Ash hopper / Bed Ash Hopper | L4 | 577000 | 0 | 0 | 0 | 1363281 | 65391 | 65391 | 0 | 0 | 1297890 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50350000 | Insulation Material/Cladding | L3 | 703800 | 0 | 0 | 0 | 703800 | 61629 | 473229 | 411600 | 0 | 230571 | 703800 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50350200 | Cladding | L4 | 703800 | 0 | 0 | 0 | 703800 | 61629 | 473229 | 411600 | 0 | 230571 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50490000 | Sootblowers | L3 | 7980000 | 0 | 0 | 0 | 7980000 | 95726 | 95726 | 0 | 0 | 7884274 | 7980000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50490100 | Soot Blower | L4 | 7980000 | 0 | 0 | 0 | 7980000 | 95726 | 95726 | 0 | 0 | 7884274 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50500000 | Boiler Mounting & Fitting | L3 | 510000 | 0 | 0 | 0 | 510000 | 59837 | 59837 | 0 | 0 | 450163 | 510000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50500200 | Silencer | L4 | 490000 | 0 | 0 | 0 | 392835 | 59835 | 59835 | 0 | 0 | 333000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50501200 | Steam traps | L4 | 20000 | 0 | 0 | 0 | 117165 | 2 | 2 | 0 | 0 | 117163 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50550000 | Spare | L3 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50550100 | Commissioning Spare | L4 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50570000 | Miscellaneous Items | L3 | 115500 | 0 | 0 | 0 | 115500 | 20985 | 30985 | 10000 | 0 | 84515 | 115500 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50570800 | Chemicals | L4 | 70500 | 0 | 0 | 0 | 18500 | 18500 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
50571100 | Boiler Name plates | L4 | 45000 | 0 | 0 | 0 | 97000 | 2485 | 12485 | 10000 | 0 | 84515 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99000000 | Common & Miscellaneous Cost Elements | L2 | 10350000 | 0 | 0 | 0 | 9400000 | 2470980.75 | 2470980.75 | 0 | 0 | 6929019.25 | 9400000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99020000 | Supervision of Erection & Commissioning | L3 | 1500000 | 0 | 0 | 0 | 1500000 | 1143599 | 1143599 | 0 | 0 | 356401 | 1500000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99020100 | Supervision of Erection & Commissioning | L4 | 1500000 | 0 | 0 | 0 | 1300000 | 943599 | 943599 | 0 | 0 | 356401 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99022500 | Site expenses | L4 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99040000 | Packing & Forwarding | L3 | 1300000 | 0 | 0 | 0 | 1700000 | 208002.26 | 208002.26 | 0 | 0 | 1491997.74 | 1700000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99040100 | Packing and Forwarding | L4 | 1300000 | 0 | 0 | 0 | 1700000 | 208002.26 | 208002.26 | 0 | 0 | 1491997.74 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99050000 | Freight | L3 | 3700000 | 0 | 0 | 0 | 3700000 | 0 | 0 | 0 | 0 | 3700000 | 3700000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99050500 | Inland Freight | L4 | 3700000 | 0 | 0 | 0 | 3700000 | 0 | 0 | 0 | 0 | 3700000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99080000 | Project Overheads / Sundry Costs | L3 | 1600000 | 0 | 0 | 0 | 1600000 | 219379.49 | 219379.49 | 0 | 0 | 1380620.51 | 1600000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99080100 | Design & Drawing Expenses | L4 | 800000 | 0 | 0 | 0 | 1069000 | 477.49 | 477.49 | 0 | 0 | 1068522.51 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99080200 | Expediting | L4 | 500000 | 0 | 0 | 0 | 231000 | 13 | 13 | 0 | 0 | 230987 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99080300 | Inspection Charges | L4 | 150000 | 0 | 0 | 0 | 150000 | 68889 | 68889 | 0 | 0 | 81111 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99080600 | Bank Charge(Supply Project) | L4 | 150000 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99100000 | Contingency | L3 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99110000 | Warranty | L3 | 900000 | 0 | 0 | 0 | 900000 | 900000 | 900000 | 0 | 0 | 0 | 0 | 900000 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99180000 | Contingency-S | L3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99250000 | Travel | L3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
99250100 | Travel - Others | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0

## JB106 11.3
Element |  | Level | Initial Total Budget | Revised Intital Total Budget | Addition/Reduction Due to Client Till Date | Addition/Reduction Due to Internal Transfer Till Date | Total Budget | Available Amount For Indenting | Available Amount For Purchase Order | Soft Allocation | Exhausted in Modified PO's | Exhausted | Distributed Amount | Undstributed Amount | Transfer To CTOH | Transfer of Savings To Contigency - S | Savings Transferred Amount | Transfered From Element | Reason Code | Revised/Trf Amount | Total To Be Transferred | Transferred From Contingency | Transferred From Contingency-S | Transferred From Warranty | Transferred From CTOH | Transfer From Freight | Transfer From P&F | Transfer From TPC | Reason For Partial Revise |  | Addition/Reduction Due to Client | Addition/Reduction Due to Internal Transfer | Remarks
1 | Total Budget | L1 | 90769680.14 | 0 | 0 | 0 | 99519679.74 | 3082121.31 | 4027921.31 | 945800 | 0 | 95491758.43 | 99519679.74 | 99519679.74 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50000000 | BOILER | L2 | 80419680.14 | 0 | 0 | 0 | 91019679.74 | 1511140.56 | 2456940.56 | 945800 | 0 | 88562739.18 | 91019679.74 | 90119679.74 | 900000 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50010000 | Drum | L3 | 1840377.11 | 0 | 0 | 0 | 1840377.11 | 152383.9 | 152383.9 | 0 | 0 | 1687993.21 | 1840377.11 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50010100 | Steam Drum and Mud drum with internals and attachm | L4 | 1840377.11 | 0 | 0 | 0 | 1840377.11 | 152383.9 | 152383.9 | 0 | 0 | 1687993.21 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50020000 | Boiler Water Wall and Circulating System Component | L3 | 33166759.65 | 0 | 0 | 0 | 33166759.65 | 0 | 0 | 0 | 0 | 33166759.65 | 33166759.65 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50020500 | Evaporator wing wall assembly | L4 | 33166759.65 | 0 | 0 | 0 | 33166759.65 | 0 | 0 | 0 | 0 | 33166759.65 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50030000 | Superheater Assembly | L3 | 2632797.51 | 0 | 0 | 0 | 2632797.51 | 0.51 | 0.51 | 0 | 0 | 2632797 | 2632797.51 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50030100 | Convection super heater Assembly(Primary-Secondary | L4 | 2632797.51 | 0 | 0 | 0 | 2632797.51 | 0.51 | 0.51 | 0 | 0 | 2632797 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50040000 | Forced Flow Assembly | L3 | 11661562.47 | 0 | 0 | 0 | 11661562.47 | 2492.12 | 2492.12 | 0 | 0 | 11659070.35 | 11661562.47 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50040100 | Forced Flow Elements assembly | L4 | 11661562.47 | 0 | 0 | 0 | 11657903.47 | 2492.12 | 2492.12 | 0 | 0 | 11655411.35 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50040500 | Header Support assembly | L4 | 0 | 0 | 0 | 0 | 3659 | 0 | 0 | 0 | 0 | 3659 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060000 | Boiler Supporting Steelworks and canopy | L3 | 5700983.4 | 0 | 0 | 0 | 12500983 | 1240057.93 | 1244257.93 | 4200 | 0 | 11256725.07 | 11600983 | 900000 | 0 | No | 0 |  |  | 0 | 900000 | 0 | 0 | 900000 | 0 | 0 | 0 | 0 | C01 | Estimation Missout/detailed de | 0 | 0
50060100 | Columns | L4 | 5400000 | 0 | 0 | 0 | 2547825 | 3700.68 | 3700.68 | 0 | 0 | 2544124.32 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060200 | Beams | L4 | 0 | 0 | 0 | 0 | 8907057.6 | 202120.01 | 202120.01 | 0 | 0 | 8704937.59 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060300 | Bracing | L4 | 0 | 0 | 0 | 0 | 100 | 99.99 | 99.99 | 0 | 0 | 0.01 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060400 | Drum lifting structure | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060600 | Structure for Canopy | L4 | 0 | 0 | 0 | 0 | 15000 | 7336.85 | 7336.85 | 0 | 0 | 7663.15 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060700 | Sheeting for Canopy | L4 | 300983.4 | 0 | 0 | 0 | 131000.4 | 126800.4 | 131000.4 | 4200 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50060800 | Fixtures for Canopy | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070000 | Gallery & Ladder | L3 | 2916400 | 0 | 0 | 0 | 4616400 | 117225.48 | 117225.48 | 0 | 0 | 4499174.52 | 4534700 | 81700 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070100 | Chequred plates | L4 | 2084400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070200 | Gratings | L4 | 0 | 0 | 0 | 0 | 2977721 | 35435.41 | 35435.41 | 0 | 0 | 2942285.59 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070300 | Ladders | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070400 | Staircases/Stair Tread | L4 | 0 | 0 | 0 | 0 | 267240 | 0.51 | 0.51 | 0 | 0 | 267239.49 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50070500 | Hand Rails | L4 | 832000 | 0 | 0 | 0 | 1289739 | 89.56 | 89.56 | 0 | 0 | 1289649.44 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50080000 | Ducting- Expansion Joint -Dampers and Supports | L3 | 378000 | 0 | 0 | 0 | 1278000 | 49154.65 | 49154.65 | 0 | 0 | 1228845.35 | 1266305 | 11695 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50080100 | FD air ducting assembly with supports | L4 | 378000 | 0 | 0 | 0 | 585805 | 0 | 0 | 0 | 0 | 585805 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50080400 | Flue Gas Ducting assembly with supports | L4 | 0 | 0 | 0 | 0 | 680500 | 37459.65 | 37459.65 | 0 | 0 | 643040.35 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090000 | Pipework | L3 | 4419000 | 0 | 0 | 0 | 4819000 | -494783.11 | 25216.89 | 520000 | 0 | 4793783.11 | 4819000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090100 | Integral Pipework | L4 | 2585000 | 0 | 0 | 0 | 3105000 | -519674.76 | 325.24 | 520000 | 0 | 3104674.76 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090400 | Boiler house Pipe works | L4 | 1834000 | 0 | 0 | 0 | 1113000 | 54.65 | 54.65 | 0 | 0 | 1112945.35 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090401 | 50 NB and above Boiler House Pipework | L5 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090402 | 40 NB and above Boiler House Pipework | L5 | 0 | 0 | 0 | 0 | 600000 | 24837 | 24837 | 0 | 0 | 575163 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090500 | Cooling water pipe work | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50090600 | Instrument air pipework | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100000 | Pipe Supports | L3 | 1253000 | 0 | 0 | 0 | 1253000 | 30466.19 | 30466.19 | 0 | 0 | 1222533.81 | 1253000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100100 | Structure & Pipe Support accessories for integral | L4 | 896000 | 0 | 0 | 0 | 646000 | -85311.81 | -85311.81 | 0 | 0 | 731311.81 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100200 | Spring Hangers for integral piping | L4 | 357000 | 0 | 0 | 0 | 133590 | 0 | 0 | 0 | 0 | 133590 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100300 | Structure & Pipe Support accessories for Boiler ho | L4 | 0 | 0 | 0 | 0 | 397180 | 115778 | 115778 | 0 | 0 | 281402 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50100400 | Spring Hangers forBoiler house piping and other pi | L4 | 0 | 0 | 0 | 0 | 76230 | 0 | 0 | 0 | 0 | 76230 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50110000 | Casing | L3 | 5353000 | 0 | 0 | 0 | 5353000 | 0.99 | 0.99 | 0 | 0 | 5352999.01 | 5353000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50110100 | Boiler Casings | L4 | 5353000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50110101 | Front Boiler Casing | L5 | 0 | 0 | 0 | 0 | 5353000 | 0.99 | 0.99 | 0 | 0 | 5352999.01 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50130000 | Seal Boxes and Sealing Arrangements | L3 | 450500 | 0 | 0 | 0 | 450500 | 30608 | 30608 | 0 | 0 | 419892 | 450500 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50130100 | Seal plate and cover plates | L4 | 450500 | 0 | 0 | 0 | 450500 | 30608 | 30608 | 0 | 0 | 419892 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50130200 | Furnace bottom sealing assembly | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50150000 | Concrete insert materials | L3 | 392000 | 0 | 0 | 0 | 392000 | 1624.92 | 1624.92 | 0 | 0 | 390375.08 | 392000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50150200 | Foundation bolts and shim plates for Boiler | L4 | 280000 | 0 | 0 | 0 | 390376 | 0.92 | 0.92 | 0 | 0 | 390375.08 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50150400 | Foundation bolts and shim plates for Auxiliary equ | L4 | 112000 | 0 | 0 | 0 | 1624 | 1624 | 1624 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50160000 | Fasteners and gaskets | L3 | 55000 | 0 | 0 | 0 | 55000 | 14620.98 | 14620.98 | 0 | 0 | 40379.02 | 55000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50160200 | Fasteners | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50160202 | Fasteners for Integral piping | L5 | 0 | 0 | 0 | 0 | 12000 | 7952 | 7952 | 0 | 0 | 4048 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50160300 | Gaskets | L4 | 55000 | 0 | 0 | 0 | 43000 | 6668.98 | 6668.98 | 0 | 0 | 36331.02 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50170000 | Boiler Rough Mountings | L3 | 264000 | 0 | 0 | 0 | 264000 | 1 | 1 | 0 | 0 | 263999 | 264000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50170100 | Standard Castings doors and fittings | L4 | 264000 | 0 | 0 | 0 | 264000 | 1 | 1 | 0 | 0 | 263999 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50210000 | Hoppers | L3 | 577000 | 0 | 0 | 0 | 1377000 | 79110 | 79110 | 0 | 0 | 1297890 | 1363281 | 13719 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50210100 | Front Ash hopper / Bed Ash Hopper | L4 | 577000 | 0 | 0 | 0 | 1363281 | 65391 | 65391 | 0 | 0 | 1297890 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50350000 | Insulation Material/Cladding | L3 | 703800 | 0 | 0 | 0 | 703800 | 61629 | 473229 | 411600 | 0 | 230571 | 703800 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50350200 | Cladding | L4 | 703800 | 0 | 0 | 0 | 703800 | 61629 | 473229 | 411600 | 0 | 230571 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50490000 | Sootblowers | L3 | 7980000 | 0 | 0 | 0 | 7980000 | 95726 | 95726 | 0 | 0 | 7884274 | 7980000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50490100 | Soot Blower | L4 | 7980000 | 0 | 0 | 0 | 7980000 | 95726 | 95726 | 0 | 0 | 7884274 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50500000 | Boiler Mounting & Fitting | L3 | 510000 | 0 | 0 | 0 | 510000 | 59837 | 59837 | 0 | 0 | 450163 | 510000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50500200 | Silencer | L4 | 490000 | 0 | 0 | 0 | 392835 | 59835 | 59835 | 0 | 0 | 333000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50501200 | Steam traps | L4 | 20000 | 0 | 0 | 0 | 117165 | 2 | 2 | 0 | 0 | 117163 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50550000 | Spare | L3 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 50000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50550100 | Commissioning Spare | L4 | 50000 | 0 | 0 | 0 | 50000 | 50000 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50570000 | Miscellaneous Items | L3 | 115500 | 0 | 0 | 0 | 115500 | 20985 | 30985 | 10000 | 0 | 84515 | 115500 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50570800 | Chemicals | L4 | 70500 | 0 | 0 | 0 | 18500 | 18500 | 18500 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
50571100 | Boiler Name plates | L4 | 45000 | 0 | 0 | 0 | 97000 | 2485 | 12485 | 10000 | 0 | 84515 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99000000 | Common & Miscellaneous Cost Elements | L2 | 10350000 | 0 | 0 | 0 | 8500000 | 1570980.75 | 1570980.75 | 0 | 0 | 6929019.25 | 8500000 | 9400000 | 900000 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99020000 | Supervision of Erection & Commissioning | L3 | 1500000 | 0 | 0 | 0 | 1500000 | 1143599 | 1143599 | 0 | 0 | 356401 | 1500000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99020100 | Supervision of Erection & Commissioning | L4 | 1500000 | 0 | 0 | 0 | 1300000 | 943599 | 943599 | 0 | 0 | 356401 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99022500 | Site expenses | L4 | 0 | 0 | 0 | 0 | 200000 | 200000 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99040000 | Packing & Forwarding | L3 | 1300000 | 0 | 0 | 0 | 1700000 | 208002.26 | 208002.26 | 0 | 0 | 1491997.74 | 1700000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99040100 | Packing and Forwarding | L4 | 1300000 | 0 | 0 | 0 | 1700000 | 208002.26 | 208002.26 | 0 | 0 | 1491997.74 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99050000 | Freight | L3 | 3700000 | 0 | 0 | 0 | 3700000 | 0 | 0 | 0 | 0 | 3700000 | 3700000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99050500 | Inland Freight | L4 | 3700000 | 0 | 0 | 0 | 3700000 | 0 | 0 | 0 | 0 | 3700000 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99080000 | Project Overheads / Sundry Costs | L3 | 1600000 | 0 | 0 | 0 | 1600000 | 219379.49 | 219379.49 | 0 | 0 | 1380620.51 | 1600000 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99080100 | Design & Drawing Expenses | L4 | 800000 | 0 | 0 | 0 | 1069000 | 477.49 | 477.49 | 0 | 0 | 1068522.51 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99080200 | Expediting | L4 | 500000 | 0 | 0 | 0 | 231000 | 13 | 13 | 0 | 0 | 230987 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99080300 | Inspection Charges | L4 | 150000 | 0 | 0 | 0 | 150000 | 68889 | 68889 | 0 | 0 | 81111 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99080600 | Bank Charge(Supply Project) | L4 | 150000 | 0 | 0 | 0 | 150000 | 150000 | 150000 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99100000 | Contingency | L3 | 1350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99110000 | Warranty | L3 | 900000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99180000 | Contingency-S | L3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99250000 | Travel | L3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0
99250100 | Travel - Others | L4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0